## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Preparation of DPR for piped water supply scheme of Kumirmora PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000454/2021-2022 | 255/HD | 07/02/2022 | 22/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 0 | 0 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kumirmora PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000559/2022-2023 | 2489/HD | 30/11/2022 | 14/01/2023 | JYOTY SOLAR POWER | 27.45 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 0.69 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1552/HD | 05/04/2023 | 05/04/2023 | Resource Division | 0.69 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 2234/HD | 14/06/2023 | 14/06/2023 | Resource Division | 10.36 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 9.79 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Electrical | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I & PH-II Howrah |  |  | BILL/01879/2022-2023 | 212 | 24/03/2023 | 24/03/2023 | WBSEDCL | 15.82 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation) along with part Laying of Distribution and Providing Functional Household Tap Connection(FHTC)for Kumirmora Piped Water Supply scheme of Udayanarayanpur Block under Howrah Division P.H.E. Dte. in the District of Howrah. (Part-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000477/2022-2023 | 2164/HD | 21/10/2022 | 08/01/2025 | PRAVAT SARKAR | 194.98 | 0 | 0 | 60
9 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000629/2022-2023 | 2810/HD | 21/12/2022 | 19/02/2023 | SAMANTA BUILDERS | 8.5 | 0 | 0 | 100
10 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Raising main & Inter Connection with both tube wells of Kumirmora PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000102/2023-2024 | 1922/HD | 08/05/2023 | 24/11/2024 | LOKENATH ENTERPRISES | 5.34 | 0 | 0 | 70
11 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000630/2022-2023 | 2807/HD | 21/12/2022 | 19/02/2023 | CHINMOY SAMANTA | 8.5 | 0 | 0 | 100
12 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 30/HD | 03/01/2024 | 03/01/2024 | Resource Division | 1.75 | 0 | 0 | 0
13 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 0.32 | 0 | 0 | 0
14 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-B) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000402/2022-2023 | 1988/HD | 26/09/2022 | 10/11/2022 | TANMOY ROY CHOUDHURY | 88.86 | 0 | 0 | 60
15 | HOWRAH | Udaynarayanpur | Electrical | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000140/2022-2023 | 3514/ED | 30/12/2022 | 01/07/2024 | M/S S R ENTERPRISE | 20.38 | 0 | 0 | 90
16 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-C) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000401/2022-2023 | 1989/HD | 26/09/2022 | 13/02/2025 | FARID UDDIN AHMED | 93.98 | 0 | 0 | 5
17 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 14/12/2025 | HORIZEN | 13.59 | 0 | 0 | 60
18 | HOWRAH | Udaynarayanpur | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Additional Laying of Distribution Pipe Lines and Providing Functional Household Tap Connection(FHTC) for leftout area of KUMIRMORA Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000248/2024-2025 | 4723/HD | 12/11/2024 | 17/06/2025 | MISHRA ENTERPRISE | 48.16 | 0 | 0 | 85
Total | [13 empty] | 552.76 | 0 | 0