## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Work Order for Preparation of DPR for new piped water supply scheme of Saoria PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/RWS/Amta II | ORD/000443/2021-2022 | 244/HD | 07/02/2022 | 22/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.86 | 2.86 | 100 | 0
2 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 24.23 | 0 | 0 | 0
3 | HOWRAH | Amta-II | Electrical | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Quotation Bill for New Service Connection at Sauria W/S. Sch. TW-I |  |  | BILL/04513/2023-2024 | 558 | 21/12/2023 | 21/12/2023 | WBSEDCL | 3.59 | 0 | 0 | 0
4 | HOWRAH | Amta-II | Electrical | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Quotation Bill for New Service Connection at Sauria W/S. Sch. TW-II |  |  | BILL/04514/2023-2024 | 557 | 21/12/2023 | 21/12/2023 | WBSEDCL | 7.61 | 0 | 0 | 0
5 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Saoria PWSS at Amta-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta2,JE/RWS/Amta II | ORD/000337/2022-2023 | 1836/HD | 08/09/2022 | 18/10/2022 | DIBAKAR SHAW | 26.67 | 26.66 | 99.96 | 100
6 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Construction of Kiosk (Two nos.) at Saoria PWSS of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Size inside 3.0 x 2.4m). | AE/Ulu | JE/BLK/amta2 | ORD/000256/2024-2025 | 1109/AE/USD | 05/11/2024 | 20/11/2024 | MAA TARA ENTERPRISE | 2.18 | 2.17 | 99.46 | 100
7 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Work Order for Laying of Distribution System(UPVC & DI), Providing Functional Household Tap Connection (FHTC), Interconnection between tube wells, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials at HW site and construction of Two storied switch room ( 5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site of SAORIA PWSS of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/BLK/amta2 | ORD/000426/2022-2023 | 2085/HD | 11/10/2022 | 23/11/2025 | KAMIRUL SK AND CO. | 370.75 | 181.56 | 48.97 | 63
8 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ |  | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 01/11/2025 | TECH VISION | 21.25 | 0 | 0 | 0
9 | HOWRAH | Amta-II | Electrical | Ground Water Based Piped Water Supply Scheme for Saoria Block- Amta-II, Dist-Howrah. | SM/11222 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saoria water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer5,Junior Engineer6 | ORD/000136/2022-2023 | 3521/ED | 30/12/2022 | 01/12/2024 | GLACIER ENGINEERING CO. | 20.25 | 19.45 | 96.05 | 90
Total | [13 empty] | 479.38 | 232.69 | 48.54