## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Khalatpur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000265/2021-2022 | 2147/HD | 01/12/2021 | 16/12/2021 | APEX ENGINEERING | 3.65 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 2113/HD | 09/11/2022 | 09/11/2022 | Resource Division | 16.9 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2023 to 30/11/2023) | AE/RWS |  | ORD/000275/2023-2024 | 392/RWS | 29/09/2023 | 29/11/2023 | DEB KUMAR DAS | 0.79 | 0 | 0 | 50
4 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1552/HD | 05/04/2023 | 05/04/2023 | Resource Division | 6.78 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000342/2022-2023 | 1854/HD | 09/09/2022 | 08/11/2022 | M/S CARE | 155.84 | 0 | 0 | 50
6 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/12/2023 to 31/01/2024) | AE/RWS |  | ORD/000335/2023-2024 | 493/RWS | 30/11/2023 | 31/01/2024 | DEB KUMAR DAS | 0.79 | 0 | 0 | 50
7 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/02/2024 to 31/03/2024) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000487/2023-2024 | 69/RWS | 31/01/2024 | 31/03/2024 | DEB KUMAR DAS | 0.79 | 0 | 0 | 100
8 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/09/2024 to 31/10/2024) |  | JE/RWS/Udaynaryanpur | ORD/000112/2024-2025 | 423/RWS | 30/08/2024 | 30/10/2024 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/04/2024 to 30/09/2024) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000720/2023-2024 | 225/RWS | 28/03/2024 | 27/09/2024 | M/S STAR CONSTRUCTION | 2.37 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Hiring of 1 no. Inspection Vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. for different PWSS in Udayanaryanpur Dev. Block, PHE Dte. Government of West Bengal (for the period from 01/07/2024 to 31/08/2024) |  | JE/RWS/Udaynaryanpur | ORD/000053/2024-2025 | 347/RWS | 28/06/2024 | 29/08/2024 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000308/2022-2023 | 1753/HD | 30/08/2022 | 29/09/2022 | LAKSHMI IRON | 28.41 | 0 | 0 | 10
12 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000309/2022-2023 | 1754/HD | 30/08/2022 | 29/09/2022 | ARINDAM ENTERPRISE | 21.71 | 0 | 0 | 30
13 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000306/2022-2023 | 1752/HD | 30/08/2022 | 29/09/2022 | BISWAJIT SAMANTA | 13.32 | 0 | 0 | 30
14 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Repairing of OHR & 2 nos Pump House(H/W & 2nd TW site) of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000079/2023-2024 | 1777/HD | 27/04/2023 | 11/06/2023 | CHANDRANI ENTERPRISE | 6.64 | 0 | 0 | 100
15 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around 2nd Pump House site of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte.. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000076/2023-2024 | 1774/HD | 27/04/2023 | 11/06/2023 | BINOY KOLEY | 5.16 | 0 | 0 | 100
16 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme in Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000439/2022-2023 | 2101/HD | 12/10/2022 | 26/11/2022 | A.K. SIKDAR | 111.19 | 0 | 0 | 30
17 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Udaynarayanpur Block of Uluberia Sub Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000651/2023-2024 | 1210/HD | 11/03/2024 | 26/03/2024 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.39 | 0 | 0 | 100
18 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 1.85 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/11/2024 to 31/12/2024) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000241/2024-2025 | 493/RWS | 30/10/2024 | 30/12/2024 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/01/2025 to 28/02/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000353/2024-2025 | 550/RWS | 31/12/2024 | 28/02/2025 | REKHA GUCHAIT | 0.78 | 0 | 0 | 0
21 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Land Development and Additional Laying of Distribution Pipe Lines with providing FHTC for leftout area for Augmentation of Khalatpur Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.(SM/11271) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000040/2024-2025 | 2862/HD | 24/06/2024 | 19/06/2025 | BISWAJIT BAG | 113.86 | 0 | 0 | 50
22 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuous work order for hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2024 to 31/03/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000181/2024-2025 | 470/RWS | 30/09/2024 | 01/04/2025 | M/S STAR CONSTRUCTION | 2.36 | 0 | 0 | 0
23 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuous work order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/05/2025 to 30/06/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000043/2025-2026 | 123/RWS | 22/04/2025 | 22/06/2025 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
24 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/04/2025 to 31/05/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000919/2024-2025 | 103/RWS | 28/03/2025 | 28/05/2025 | SANJIB BARMAN | 0.79 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/03/2025 to 30/04/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000646/2024-2025 | 57/RWS | 27/02/2025 | 29/04/2025 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
26 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/06/2025 to 31/07/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000079/2025-2026 | 178/A/RWS | 27/05/2025 | 27/07/2025 | SANJIB BARMAN | 0.79 | 0 | 0 | 0
27 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Construction of Boundary Wall, Land Development at HEAD WORK Site, Additional Laying of Distribution Pipe Lines at UTTAR MANASRI Piped Water Supply Scheme and Additional Laying of Distribution Pipe Lines at KHALATPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000012/2025-2026 | 1855/HD | 16/04/2025 | 10/02/2026 | SAMIRON GHOSH | 96.34 | 0 | 0 | 40
28 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/07/2025 to 31/08/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000106/2025-2026 | 215/RWS | 30/06/2025 | 31/08/2025 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
29 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/08/2025 to 30/09/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000137/2025-2026 | 260/RWS | 30/07/2025 | 29/09/2025 | SANJIB BARMAN | 0.79 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/09/2025 to 31/10/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000154/2025-2026 | 276/RWS | 21/08/2025 | 21/10/2025 | REKHA GUCHAIT | 0.79 | 0 | 0 | 0
31 | HOWRAH |  | Howrah Division | Augmentation of Khalatpur PWSS | SM/11271 | Augmentation | Work Order for Constrcution of 1.5 mtrs. Height Boundary Wall along with 750mm Height 3 layer barbed wire around head work site of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000077/2023-2024 | 1775/HD | 27/04/2023 | 10/09/2024 | MAITY CONSTRUCTIONS | 13.8 | 0 | 0 | 90
Total | [13 empty] | 612.6 | 0 | 0