## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Preparation of DPR for new piped water supply scheme of Sonamui PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000437/2021-2022 | 238/HD | 07/02/2022 | 22/02/2022 | RADIANT | 3.61 | 3.61 | 100 | 0
2 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sonamui PWSS of Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000600/2022-2023 | 2716/HD | 14/12/2022 | 28/01/2023 | AQUATECH ENGINEERS | 36.21 | 35.81 | 98.88 | 0
3 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) | AE/Ulu | je/blk/bagn1 | ORD/000523/2022-2023 | 2368/HD | 18/11/2022 | 02/01/2023 | M/S MOINAK POREL | 90 | 81.22 | 90.25 | 100
4 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | AE/Ulu | JE/USD | ORD/000521/2022-2023 | 2366/HD | 18/11/2022 | 02/01/2023 | S RAHA ENTERPRISE | 82.51 | 78.81 | 95.51 | 100
5 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/Ulu | JE/USD | ORD/000522/2022-2023 | 2367/HD | 18/11/2022 | 02/01/2023 | BISWAJIT BAG | 86.2 | 85.57 | 99.27 | 100
6 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Sonamui PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000097/2023-2024 | 1946/HD | 10/05/2023 | 09/07/2023 | KALIDAS ENTERPRISE | 7.18 | 7.18 | 100 | 100
7 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 56.07 | 0 | 0 | 0
8 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1698/HD | 21/04/2023 | 21/04/2023 | Resource Division | 3.22 | 0 | 0 | 0
9 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 2753/HD | 28/07/2023 | 28/07/2023 | Resource Division | 15.4 | 0 | 0 | 0
10 | HOWRAH | Amta-I | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Quotation Bill for New Service Connection at Sonamui W/S. Sch. PH-I |  |  | BILL/00835/2023-2024 | 59 | 05/06/2023 | 05/06/2023 | WBSEDCL | 0.21 | 0 | 0 | 0
11 | HOWRAH | Amta-I | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | New Service Connection at Sonamui W/S. SCh. PH-I |  |  | BILL/00774/2023-2024 | 47 | 24/05/2023 | 24/05/2023 | WBSEDCL | 17.81 | 0 | 0 | 0
12 | HOWRAH | Amta-I | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Quotation Bill for New Service Connection at Sonamui W/S. Sch. PH-II |  |  | BILL/00775/2023-2024 | 47 | 24/05/2023 | 24/05/2023 | WBSEDCL | 10.43 | 0 | 0 | 0
13 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-21) | AE/Ulu | JE/USD | ORD/000534/2022-2023 | 2379/HD | 18/11/2022 | 18/12/2022 | A.N ROY & CO | 10.15 | 8.67 | 85.43 | 100
14 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-11) | AE/Ulu | JE/USD | ORD/000506/2022-2023 | 2254/HD | 04/11/2022 | 04/12/2022 | ABONTICA ENTERPRISE | 20.83 | 15.33 | 73.6 | 100
15 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-2) | AE/Ulu | JE/USD | ORD/000493/2022-2023 | 2245/HD | 04/11/2022 | 04/12/2022 | AMIT CONSTRUCTION | 32.09 | 22.13 | 68.97 | 100
16 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | AE/Ulu | JE/USD | ORD/000524/2022-2023 | 2369/HD | 18/11/2022 | 02/01/2023 | JAI BHARAT COMMERCIAL CORPORATION | 79.6 | 43.03 | 54.05 | 100
17 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-13) | AE/Ulu | JE/USD | ORD/000526/2022-2023 | 2371/HD | 18/11/2022 | 18/12/2022 | BINOY KOLEY | 10.13 | 8.67 | 85.59 | 100
18 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Oder for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-9) | AE/Ulu | JE/USD | ORD/000502/2022-2023 | 2252/HD | 04/11/2022 | 04/12/2022 | ABONTICA ENTERPRISE | 20.76 | 18.9 | 91.02 | 100
19 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-10) | AE/Ulu | JE/USD | ORD/000503/2022-2023 | 2253/HD | 04/11/2022 | 04/12/2022 | UNIVERSAL CONSTRUCTION | 20.72 | 15.14 | 73.07 | 100
20 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme in Amta-I Block under Howrah Division, PHE Dte.(Part-5) | AE/Ulu | JE/USD | ORD/000496/2022-2023 | 2248/HD | 04/11/2022 | 04/12/2022 | M/S B.S.P. ENTERPRISES | 33.03 | 23.98 | 72.59 | 100
21 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-12) | AE/Ulu | JE/USD | ORD/000525/2022-2023 | 2370/HD | 18/11/2022 | 18/12/2022 | S.M. CONSTRUCTION | 10.15 | 9.02 | 88.83 | 100
22 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-14) | AE/Ulu | JE/USD | ORD/000527/2022-2023 | 2372/HD | 18/11/2022 | 18/12/2022 | M/S AHAMED CONSTRUCTION | 10.06 | 7.62 | 75.75 | 100
23 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-15) | AE/Ulu | JE/USD | ORD/000528/2022-2023 | 2373/HD | 18/11/2022 | 18/12/2022 | MONIRUL ISLAM | 10.01 | 7.62 | 76.17 | 100
24 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-16) | AE/Ulu | JE/USD | ORD/000529/2022-2023 | 2374/HD | 18/11/2022 | 18/12/2022 | MAITY CONSTRUCTIONS | 9.7 | 8.11 | 83.59 | 100
25 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Oder for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-8) | AE/Ulu | JE/USD | ORD/000501/2022-2023 | 2251/HD | 04/11/2022 | 04/12/2022 | MS ARPAN ENTERPRISE | 20.64 | 17.62 | 85.38 | 100
26 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-18) | AE/Ulu | JE/USD | ORD/000531/2022-2023 | 2376/HD | 18/11/2022 | 18/12/2022 | ADRIJA ENTERPRISE | 10.09 | 7.62 | 75.52 | 100
27 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-6) | AE/Ulu | JE/USD | ORD/000497/2022-2023 | 2249/HD | 04/11/2022 | 04/12/2022 | S.S ENTERPRISE | 20.52 | 17.25 | 84.02 | 100
28 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-19) | AE/Ulu | JE/USD | ORD/000532/2022-2023 | 2377/HD | 18/11/2022 | 18/12/2022 | KRISH CONSTRUCTION | 10.16 | 8.74 | 86 | 100
29 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-20) | AE/Ulu | JE/USD | ORD/000533/2022-2023 | 2378/HD | 18/11/2022 | 18/12/2022 | DEBABRATA CHAKRABORTY | 10.16 | 9.01 | 88.63 | 100
30 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-1)Number of FHTC to be provided (Approx):320 | AE/Ulu | JE/USD | ORD/000632/2022-2023 | 2990/HD | 29/12/2022 | 28/01/2023 | RANA ENTERPRISE | 34.79 | 22.01 | 63.25 | 100
31 | HOWRAH | Amta-I | Electrical | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sonamui water supply scheme, T.W. No.- I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/000134/2022-2023 | 3524/ED | 30/12/2022 | 30/03/2023 | SANKAR PRASAD DUTTA & CO. | 22.35 | 22.35 | 100 | 100
32 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-7) | AE/Ulu | JE/USD | ORD/000500/2022-2023 | 2250/HD | 04/11/2022 | 04/12/2022 | ABONTICA ENTERPRISE | 20.72 | 19.13 | 92.34 | 100
33 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Sonamui PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000096/2023-2024 | 1945/HD | 10/05/2023 | 09/07/2023 | M/S KANIKA ROY ENTERPRISE | 7.18 | 7.18 | 100 | 100
34 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work order for Interconnection between Tube wells & OHR at Sonamui Water Supply scheme at Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000098/2023-2024 | 1947/HD | 10/05/2023 | 09/07/2023 | BHOLA NATH CONSTRUCTION | 13.13 | 12.03 | 91.59 | 100
35 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-17) | AE/Ulu | JE/USD | ORD/000530/2022-2023 | 2375/HD | 18/11/2022 | 18/12/2022 | APEX ENGINEERING | 10.12 | 8.08 | 79.87 | 95
36 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Land Development & Approach Road at 2nd TW site of Sonamoi PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu | JE/USD | ORD/000386/2024-2025 | 1294/AE/USD | 17/12/2024 | 27/03/2025 | APST TASTIC DEVELOPERS PRIVATE LIMITED | 0.86 | 0 | 0 | 100
37 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Construction of boundary wall at HW Site of Sonamoi W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000006/2025-2026 | 1810/HD | 08/04/2025 | 07/06/2025 | M/S JOY | 29.15 | 0 | 0 | 0
38 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ |  | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 01/11/2025 | TECH VISION | 21.25 | 0 | 0 | 0
39 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-3) | AE/Ulu | JE/USD | ORD/000494/2022-2023 | 2246/HD | 04/11/2022 | 03/08/2024 | N. G ENGINEERING | 32.94 | 0 | 0 | 100
40 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir as Per Departmental Design including Soil Investigation, Laying Distribution Pipeline for Sonamui PWSS of Amta-I Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | ORD/000612/2022-2023 | 2676/HD | 12/12/2022 | 01/12/2024 | M/S JOY | 244.66 | 175.48 | 71.72 | 100
41 | HOWRAH | Amta-I | Howrah Division | Ground Water Based Sonamui PWSS to Accommodate FHTC in Amta-I Block within Howrah District Under Howrah Division PHE Dte. | SM/11458 | New | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-4) | AE/Ulu | JE/USD | ORD/000495/2022-2023 | 2247/HD | 04/11/2022 | 24/10/2024 | M/S ASHIRBAD (INDIA) | 32.95 | 0 | 0 | 100
Total | [13 empty] | 1217.8 | 806.94 | 66.26