## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Preparation of DPR for Augmentation of Par-Radhanagar PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000256/2022-2023 | 330/AE/USD | 16/08/2022 | 30/09/2022 | STEELCONC AND ASSOCIATES | 3.29 | 3.16 | 96.07 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at PerRadhanagar PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000561/2022-2023 | 2491/HD | 30/11/2022 | 14/01/2023 | WATER TECH | 36.22 | 30.78 | 85 | 100
3 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 14.26 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 2716/HD | 25/07/2023 | 25/07/2023 | Resource Division | 13.78 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 19.05 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Electrical | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Quotation bill for New Service Connection at Par-Radhanagar Water Supply Scheme. |  |  | BILL/04051/2023-2024 | 331 | 06/10/2023 | 06/10/2023 | WBSEDCL | 2.67 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Electrical | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Quotation Bill for New Service Connection at Par-Radhanagar |  |  | BILL/01884/2022-2023 | 228 | 29/03/2023 | 29/03/2023 | WBSEDCL | 8.72 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Per-radhanagar W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000622/2022-2023 | 2802/HD | 21/12/2022 | 19/02/2023 | BINOY KOLEY | 7.83 | 7.29 | 93.16 | 98
9 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Work Order for Construction of Pump House (5.40m x 3.60m) with water supply & sanitary arrangement at HW site Per Radhanagar W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000625/2022-2023 | 2805/HD | 21/12/2022 | 19/02/2023 | M/S M.K. MONDAL | 7.83 | 7.3 | 93.16 | 95
10 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 29/HD | 03/01/2024 | 03/01/2024 | Resource Division | 0.87 | 0 | 0 | 0
11 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 1.13 | 0 | 0 | 0
12 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of PER RADHANAGAR Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B) Mouza-Peruhareshpur | AE/RWS | JE/BLK/amta2,JE/RWS/Udaynaryanpur | ORD/000432/2022-2023 | 2108/HD | 13/10/2022 | 01/04/2025 | GHOSH ENTERPRISE. | 149.58 | 67.7 | 45.26 | 65
13 | HOWRAH | Udaynarayanpur | Electrical | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Per Radhanagr water supply scheme, T.W. No. III & IV, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000255/2022-2023 | 922/ED | 22/02/2023 | 01/04/2024 | GLACIER ENGINEERING CO. | 21.83 | 21.58 | 98.84 | 80
14 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Rising main & Inter Connection with both tube wells of Per Radhanagar PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/BLK/AMTA2 | ORD/000558/2023-2024 | 904/HD | 27/02/2024 | 26/05/2024 | KUNAL BANERJEE | 6.28 | 5.56 | 88.6 | 100
15 | HOWRAH | Udaynarayanpur | Howrah Division | PER RADHANAGAR PIPED WATER SUPPLY SCHEME WITH FHTC | SM/11572 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at 2nd TW Site and Estimate for Additional Laying of Distribution Pipe Lines for leftout area of PER RADHANAGAR (Part-B) Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/BLK/amta2 | ORD/000148/2024-2025 | 4118/HD | 23/09/2024 | 21/01/2025 | GHOSH ENTERPRISE | 72.21 | 0 | 0 | 100
Total | [13 empty] | 365.55 | 143.38 | 39.22