## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT Udaynarayanpur Block UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000228/2022-2023 | 380/CMSD-I | 05/08/2022 | 20/08/2022 | DEY ENTERPRISE | 4.67 | 0 | 0 | 0
2 | HOWRAH | Udaynarayanpur | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UDAYNARAYANPUR W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DIVISION, PHE DTE. |  |  | ORD/000230/2022-2023 | 379/CMSD-I | 05/08/2022 | 20/08/2022 | DEY ENTERPRISE | 4.51 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | PROVIDING DRILLING CREW AND OTHERS MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR UDAYNARAYANPUR W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000231/2022-2023 | 378/CMSD-I | 05/08/2022 | 20/08/2022 | DEY ENTERPRISE | 4.57 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | PROVIDING DRILLING CREWS AND OTHERS MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR GAURANGA CHAK W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000257/2022-2023 | 378/ CMSD-I | 05/08/2022 | 20/08/2022 | DEY ENTERPRISE | 4.57 | 4.35 | 95.1 | 0
5 | HOWRAH | Udaynarayanpur | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT GAURANGA CHAK W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000258/2022-2023 | 380/ CMSD-I | 05/08/2022 | 20/08/2022 | DEY ENTERPRISE | 4.67 | 3.92 | 83.76 | 0
6 | HOWRAH | Udaynarayanpur | Central Drilling | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT GAURANGA CHAK W/S SCH, UDAYNARAYANPUR BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000259/2022-2023 | 379/ CMSD-I | 05/08/2022 | 20/08/2022 | DEY ENTERPRISE | 4.51 | 4.51 | 100 | 0
7 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gaurangachak PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000557/2022-2023 | 2487/HD | 30/11/2022 | 14/01/2023 | PRANTIK DRILLING AGENCY | 36.08 | 31.75 | 88 | 0
8 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Preparation of DPR for new piped water supply scheme of Gourangachak PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000257/2022-2023 | 331/AE/USD | 16/08/2022 | 30/09/2022 | STEELCONC AND ASSOCIATES | 3.29 | 3.15 | 95.76 | 0
9 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 2.38 | 0 | 0 | 0
10 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1552/HD | 05/04/2023 | 05/04/2023 | Resource Division | 3.11 | 0 | 0 | 0
11 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 2234/HD | 14/06/2023 | 14/06/2023 | Resource Division | 8.22 | 0 | 0 | 0
12 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 15.87 | 0 | 0 | 0
13 | HOWRAH | Udaynarayanpur | Electrical | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Quotation Bill for New Service Connection at Gourangachak Pwss I & II |  |  | BILL/01885/2022-2023 | 227 | 29/03/2023 | 29/03/2023 | WBSEDCL | 11.63 | 0 | 0 | 0
14 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Work Order Construction of Pump House ( 5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Gourangachak W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000621/2022-2023 | 2801/HD | 21/12/2022 | 19/02/2023 | SAIKAT ENTERPRISE | 7.84 | 7.31 | 93.2 | 100
15 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Gourangachak W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,je1_how_how,JE Sadar | ORD/000624/2022-2023 | 2804/HD | 21/12/2022 | 19/02/2023 | SONAR BANGLA ENTERPRISE | 7.6 | 7.49 | 98.5 | 100
16 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Work Order for Raising main & Inter Connection with both tube wells of Gauranga Chak PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000101/2023-2024 | 1921/HD | 08/05/2023 | 07/06/2023 | SONAR BANGLA ENTERPRISE | 5.19 | 5.08 | 97.82 | 100
17 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 27/HD | 03/01/2024 | 03/01/2024 | Resource Division | 0.52 | 0 | 0 | 0
18 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 3.7 | 0 | 0 | 0
19 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site and Additional Laying of Distribution Pipe Lines with providing FHTC at GOURANGACHAK Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.(SM/11573) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000041/2024-2025 | 2884/HD | 25/06/2024 | 17/10/2025 | PRADIP KUMAR JATI | 149.89 | 0 | 0 | 40
20 | HOWRAH | Udaynarayanpur | Howrah Division | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Additional Laying of Distribution Pipe Lines for leftout area of GOURANGACHAK Piped Water Supply Scheme in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS |  | ORD/000017/2025-2026 | 1938/HD | 22/04/2025 | 21/06/2025 | PRADIP KUMAR JATI | 61.73 | 0 | 0 | 0
21 | HOWRAH | Udaynarayanpur | Electrical | Gauranga Chak Piped Water Supply Scheme with FHTC, Udaynarayanpur Block. | SM/11573 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gauranga Chak water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000143/2022-2023 | 3508/ED | 30/12/2022 | 01/03/2024 | P.P. CONCERN | 20.36 | 19.97 | 98.09 | 30
Total | [13 empty] | 364.92 | 87.51 | 23.98