## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Tulsiberia PWSS of Uluberia-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000599/2022-2023 | 2715/HD | 14/12/2022 | 28/01/2023 | ACME CONSTRUCTION | 36.15 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Preparation of DPR for new piped water supply scheme of Tulshiberia PWSS, Uluberia-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu | JE/USD | ORD/000361/2022-2023 | 456/AE/USD | 15/09/2022 | 30/10/2022 | DULAL MAJUMDER | 3.13 | 0 | 0 | 0
3 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Work order for Interconnection between Tube wells & OHR at Tulsiberia Water Supply scheme at Uluberia-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000099/2023-2024 | 1948/HD | 10/05/2023 | 09/07/2023 | SUNIL ENTERPRISE | 10.42 | 0 | 0 | 100
4 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 20.18 | 0 | 0 | 0
5 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1698/HD | 21/04/2023 | 21/04/2023 | Resource Division | 5.48 | 0 | 0 | 0
6 | HOWRAH | Uluberia-II | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Deposition of Quotation money for Tulshiberia w/s scheme, P.H No-I ,Dist-howrah under ED PHED. |  |  | BILL/01065/2023-2024 | 76 | 15/06/2023 | 15/06/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
7 | HOWRAH | Uluberia-II | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Quotation Bill for New Service Connection at Tulsiberia Kalimandir W/S. Sch. PH-I & II |  |  | BILL/00718/2023-2024 | 18 | 02/05/2023 | 02/05/2023 | WBSEDCL | 11.36 | 0 | 0 | 0
8 | HOWRAH | Uluberia-II | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001104/2023-2024 | 2830/HMSD | 30/10/2023 | 29/04/2024 | SANJIB PRADHAN | 0.86 | 0 | 0 | 42
9 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 530/HD | 06/02/2024 | 06/02/2024 | Resource Division | 11.09 | 0 | 0 | 0
10 | HOWRAH | Uluberia-II | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Supply of Fuel for 1(One) no Diesel Luxury taxi on contract Carriage for the Office of the Assistant Engineer,Howrah Mechanical Sub Division PHE Dte.(JJM Work for Hooghly District) for the Month of March 2024. |  |  | BILL/00263/2024-2025 | 106 | 07/05/2024 | 07/05/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
11 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Construction of boundary wall at HW Site of Tulsiberia W/S scheme within Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000453/2024-2025 | 988/HD | 20/02/2025 | 21/04/2025 | SANJOY GHOSH | 27.81 | 0 | 0 | 0
12 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Construction of 2.50 mtrs. Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 4 layer barbed wire fencing around 2nd. TW site including with land development & approach road of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub-Division under Howrah Division, PHE. Dte. | AE/Ulu | JE-USD | ORD/000734/2024-2025 | 1353/HD | 11/03/2025 | 04/12/2025 | A.A ENTERPRISE | 9.3 | 0 | 0 | 85
13 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Land Development and Approach Road at HW site of Tulsiberia PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu |  | ORD/000004/2025-2026 | 1826/HD | 09/04/2025 | 09/05/2025 | MUKHERJEE CONSTRUCTION | 9.01 | 0 | 0 | 0
14 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Land Development & Approach Road at 2nd TW site of Tulsiberia PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu | JE/USD | ORD/000416/2024-2025 | 1491/AE/USD | 16/01/2025 | 05/02/2025 | MM ENTERPRISE | 1.19 | 0 | 0 | 0
15 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Construction of Pump House (3.60m x 3.30m) with water supply arrangement at Head Work site of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu | JE-USD | ORD/000009/2025-2026 | 1811/HD | 08/04/2025 | 23/05/2025 | ARUP NANDY | 6.47 | 0 | 0 | 15
16 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Construction of 1.8 mtrs. Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 4 layer barbed wire fencing around head work site including land development & approach road of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub Division under Howrah Division, PHE. Dte. | AE/Ulu | JE-USD | ORD/000011/2025-2026 | 1812/HD | 08/04/2025 | 07/06/2025 | ARUP NANDY | 24.85 | 0 | 0 | 10
17 | HOWRAH | Uluberia-II | Howrah Division | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-II & Uluberia-II Block) | AE HQ |  | ORD/000222/2025-2026 | 4120/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
18 | HOWRAH | Uluberia-II | Electrical | Tulsiberia Piped Water Supply Scheme with provision of FHTC. | SM/11574 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tulsiberia water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000133/2022-2023 | 3525/ED | 30/12/2022 | 23/10/2024 | TAMAL ENTERPRISE | 20.35 | 0 | 0 | 30
Total | [13 empty] | 206.94 | 0 | 0