## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nayachak water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000150/2022-2023 | 3518/ED | 30/12/2022 | 30/03/2023 | JAGANNATH ENTERPRISE | 21.36 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nayachak water supply scheme, T.W. No. III, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000882/2023-2024 | 3455/ED | 11/08/2023 | 09/11/2023 | TAMAL ENTERPRISE | 10.76 | 0 | 0 | 0
3 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 160.85 | 0 | 0 | 0
4 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 159.48 | 0 | 0 | 0
5 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 7.39 | 0 | 0 | 0
6 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Laying Distribution Pipe Lines(UPVC & DI) With Allied Works and Providing Household Functional Tap Connection & Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials including foundation design for NAYACHAK PWSS OF ULUBERIA-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE-USD | ORD/000141/2023-2024 | 2808/HD | 03/08/2023 | 02/08/2025 | GUPTA ENTERPRISE | 775.72 | 257.45 | 33.19 | 60
7 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nayachak PWSS of Uluberia-II block of Uluberia Sub Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE-USD | ORD/000601/2022-2023 | 2717/HD | 14/12/2022 | 03/04/2025 | AQUATECH ENGINEERS | 54.31 | 0 | 0 | 100
8 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Material Requisition To Resource Division |  |  | RTOR000046/2024-2025 | 494/HD | 24/01/2025 | 24/01/2025 | Resource Division | 12.32 | 0 | 0 | 0
9 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Material Requisition To Resource Division |  |  | RTOR000071/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 1.23 | 0 | 0 | 0
10 | HOWRAH | Uluberia-II | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Quotation money deposition for new service connection at Nayachak w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008292212 Reference ID- 106877189 SM Code- 11641 |  |  | BILL/02852/2024-2025 | 676 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.98 | 0 | 0 | 0
11 | HOWRAH | Uluberia-II | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Quotation money deposition for new service connection at Nayachak w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008293364 Reference ID- 106877855 SM Code- 11641 |  |  | BILL/02853/2024-2025 | 677 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.81 | 0 | 0 | 0
12 | HOWRAH | Uluberia-II | Electrical | Ground Water Based Piped Water Supply Scheme for NAYACHAK, Block- Uluberia-II, Howrah. | SM/11641 | New | Quotation money deposition for new service connection at Nayachak w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008296018 Reference ID- 106879922 SM Code- 11641 |  |  | BILL/04302/2024-2025 |  | 20/03/2025 | 20/03/2025 | WBSEDCL | 6.67 | 0 | 0 | 0
Total | [13 empty] | 1217.89 | 257.45 | 21.14