## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Bipro Noapara PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000220/2022-2023 | 79/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.89 | 3.89 | 100 | 0
2 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 21.49 | 0 | 0 | 0
3 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 43.47 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bipra Noapara water supply scheme, T.W. No.- I & II, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000117/2022-2023 | 3507/ED | 30/12/2022 | 30/03/2023 | MAA KALI ENTERPRISE | 22.83 | 21.41 | 93.8 | 40
5 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Work Order for Sinking of 4 (Four) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bipra Noapara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000661/2022-2023 | 171/HD | 13/01/2023 | 27/02/2023 | M DHARA AND BROTHERS | 51.16 | 12.21 | 23.87 | 25
6 | HOWRAH | Domjur | Electrical | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bipra Noapara water supply scheme, T.W. No.- III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000861/2023-2024 | 3433/ED | 11/08/2023 | 09/11/2023 | MAA KALI ENTERPRISE | 21.49 | 0 | 0 | 30
7 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Jagatballavpur and Domjur Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000550/2023-2024 | 846/HD | 22/02/2024 | 08/03/2024 | TRIMARV SOLUTIONS PRIVATE LIMITED | 4.85 | 4.85 | 100 | 100
8 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 4769/HD | 14/11/2024 | 14/11/2024 | Resource Division | 33.74 | 0 | 0 | 0
9 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 3589/HD | 13/08/2024 | 13/08/2024 | Resource Division | 6.33 | 0 | 0 | 0
10 | HOWRAH | Domjur | Electrical | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Quotation money deposition for new service connection at P.H No.-II of Bipra Noapara pwss, Dist- Howrah under ED PHED. App. No.-1007764053 SM/11711 |  |  | BILL/00457/2024-2025 | 134 | 17/05/2024 | 17/05/2024 | WBSEDCL | 7.48 | 0 | 0 | 0
11 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Restoration work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 2.1 kmp to 3.5 kmp( due to Cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-2025 |  |  | BILL/00826/2024-2025 | BP-2024-25-494 | 27/11/2024 | 27/11/2024 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 5.33 | 0 | 0 | 0
12 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | 2Nos Construction of Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Site, Reparing of 2 nos ExistingPump House 3rd & 4th TW site (3.60m x 3.00 m), Construction of Boundary Wall at 1st Tube Well Site (30 m X 20 m), 3 nos Boundary Wall at 2nd, 3rd & 4th Tube Well Site (12 m X 12 m), Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 4th Pump House, 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Bipra Noapara at PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000134/2023-2024 | 2713/HD | 25/07/2023 | 24/07/2026 | B.B.C ENTERPRISE | 556.42 | 238.94 | 42.94 | 82
13 | HOWRAH | Domjur | Howrah Division | Bipra Noapara PWSS with provision of FHTC Connection Block-Domjur, Howrah. | SM/11711 | New | Laying of additional distribution pipeline and road restoration at Bipro Naopara PWSS at Domjur Block under Howrah Sadar Sub Division of Howrah Division, PHE Dte. (SM/11711) | AE/SADAR | je1_iu | ORD/000720/2024-2025 | 1322/HD | 10/03/2025 | 09/05/2025 | B.B.C ENTERPRISE | 106.17 | 0 | 0 | 30
Total | [13 empty] | 884.67 | 281.32 | 31.8