## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | SM/11717 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Chandrapur PWSS of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/RWS/Bagnan I,JE/USD | ORD/000603/2022-2023 | 2719/HD | 14/12/2022 | 28/01/2023 | SPG ENTERPRISES | 27.49 | 0 | 0 | 50
2 | HOWRAH | Bagnan-I | Electrical | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | SM/11717 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chandrapur water supply scheme, T.W. No. I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000284/2022-2023 | 934/ED | 22/02/2023 | 23/05/2023 | KARUNAMOY ENGINEERING | 21.49 | 0 | 0 | 0
3 | HOWRAH | Bagnan-I | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | SM/11717 | New | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 31.28 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | SM/11717 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 29.1 | 0 | 0 | 0
5 | HOWRAH | Bagnan-I | Electrical | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | SM/11717 | New | QUOTATION FOR NEW POWER CONNECTION FOR CHANDRAPUR PWSS PH NO-II |  |  | BILL/02977/2023-2024 | 216 | 24/08/2023 | 24/08/2023 | WBSEDCL | 7.33 | 0 | 0 | 0
6 | HOWRAH | Bagnan-I | Howrah Division | Chandrapur Piped Water Supply Scheme with provision of FHTC, Block - Bagnan-I, Howrah. | SM/11717 | New | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC)(Mouza-Chandrapur (58) & Interconnection for 2nd TW and 1st Tube well (HW site)& Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials (Drawing No.PC-I/OHR/07/2012 (Sheet No.1&2) with Soil test & Design for Chandrapur PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. | AE/Ulu | je/blk/bagn1 | ORD/000043/2023-2024 | 1746/HD | 25/04/2023 | 07/08/2026 | K.M. ENTERPRISE | 300.94 | 0 | 0 | 0
Total | [13 empty] | 417.64 | 0 | 0