## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | SM/11718 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ulanpara PWSS of Bagnan I Block Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu |  | ORD/000598/2022-2023 | 2714/HD | 14/12/2022 | 28/01/2023 | AUXILIARY TUBEWELL DRILLERS | 36.22 | 0 | 0 | 0
2 | HOWRAH | Bagnan-I | Electrical | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | SM/11718 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ulanpara water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000132/2022-2023 | 3526/ED | 30/12/2022 | 30/03/2023 | M/S, GHOSH ENTERPRISE | 21.37 | 0 | 0 | 0
3 | HOWRAH | Bagnan-I | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | SM/11718 | New | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC), Interconnection for 2nd TW and 1st Tube well (HW site) & Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref: Dept. Super Struc. DRG. No. PC I/OHR/11/2012) Including All pipe Connection including foundation design for ULANPARA PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE | AE/Ulu |  | ORD/000017/2023-2024 | 1651/HD | 18/04/2023 | 17/04/2024 | SUDHAMAY MAJUMDAR | 361.15 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | SM/11718 | New | Work Order for Preparation of DPR for new piped water supply scheme of Ulanpara PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE-USD,JE/RWS/Bagnan I | ORD/000449/2021-2022 | 250/HD | 07/02/2022 | 22/02/2022 | DULAL MAJUMDER | 2.69 | 2.69 | 100 | 100
5 | HOWRAH | Bagnan-I | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | SM/11718 | New | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 48.67 | 0 | 0 | 0
6 | HOWRAH | Bagnan-I | Howrah Division | Ulanpara Piped Water Supply Scheme with provision of FHTC Block- Bagnan-I, Howrah. | SM/11718 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 42.67 | 0 | 0 | 0
Total | [13 empty] | 512.77 | 2.69 | 0.53