## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Work Order for Preparation of DPR for new piped water supply scheme of Jikira PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/RWS/Amta II | ORD/000441/2021-2022 | 242/HD | 07/02/2022 | 22/02/2022 | VOYAGER | 3.36 | 3.36 | 100 | 0
2 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Jagadishpur G.P Area) Zone-14 Length= 536.00mtr.(PART-A) | AE/Ulu | JE/RWS/Amta II | ORD/000246/2020-2021 | 1194/HD | 30/09/2020 | 30/10/2020 | ADITYA HAZRA | 3.12 | 0 | 0 | 0
3 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 21.53 | 0 | 0 | 0
4 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta2,JE/USD | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 25/11/2023 | PRANTIK DRILLING AGENCY | 77.89 | 23.53 | 30.21 | 100
5 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 8.13 | 0 | 0 | 0
6 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-I |  |  | BILL/04630/2023-2024 | 619 | 08/01/2024 | 08/01/2024 | WBSEDCL | 3.86 | 0 | 0 | 0
7 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-III |  |  | BILL/05720/2023-2024 | 709 | 25/01/2024 | 25/01/2024 | WBSEDCL | 12.37 | 0 | 0 | 0
8 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Quotation for Pole Shifting of Jhikira w/s Scheme,PH No-I under Electrical Division,PHE Dte(SM/11719) Application Id-100000105833. Reference Id-860297815. |  |  | BILL/00234/2024-2025 | 84 | 22/04/2024 | 22/04/2024 | WBSEDCL | 0.36 | 0 | 0 | 0
9 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation,Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site, Laying Distribution Pipeline & Providing FHTC (3205 nos) for Jhikira Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/BLK/amta2 | ORD/000563/2022-2023 | 2501/HD | 30/11/2022 | 18/05/2025 | K.P. CONSTRUCTION | 616.01 | 311.05 | 50.49 | 62
10 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JHIKIRA water supply scheme, TW No. III, Block: Amta-II, District - Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003101/2024-2025 | 486/ED | 18/03/2025 | 16/06/2025 | STANDARD ELECTRICALS | 11.3 | 0 | 0 | 0
11 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Construction of Boundary Wall (120 m Length) at 1st Tubewell Site, (66 m Length) at 2nd Tubewell Site & (52 m Length) at 3rd Tubewell Site, Construction of Approach Road with Paver Block from existing road to Head Work Site, Land Development of 3rd TW Site, construction of 1 nos switch room (3.6m x 3.00m) with water supply & sanitary arrangement at 3rd Tubewell site and Interconnection work with 3rd T. well of Jhikra PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000094/2025-2026 | 2885/HD | 23/06/2025 | 21/09/2025 | K.P. CONSTRUCTION | 75.36 | 0 | 0 | 0
12 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Sinking of additional 1 (One) Nos. (250 X 150 mm) Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jhikira PWSS at Amta-II Block in Uluberia Sub-Division, under Howrah Division PHE Dte. (Location: Jhikira) | AE/Ulu | JE/RWS/Amta II | ORD/000586/2024-2025 | 1175/HD | 03/03/2025 | 17/04/2025 | PRANTIK DRILLING AGENCY | 14.71 | 0 | 0 | 100
13 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Land Development of Head work site with laying of distribution pipe line within Jhikra PWSS at Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000093/2025-2026 | 2884/HD | 23/06/2025 | 21/09/2025 | K.P. CONSTRUCTION | 81.48 | 0 | 0 | 0
14 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ |  | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 01/11/2025 | TECH VISION | 21.25 | 0 | 0 | 0
15 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Jhikira PWSS, Under Howrah Division, Block Amta-II District-Howrah. | SM/11719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jhikira water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer5 | ORD/000256/2022-2023 | 923/ED | 22/02/2023 | 28/09/2024 | STANDARD ELECTRICALS | 22.61 | 21.89 | 96.79 | 70
Total | [13 empty] | 973.35 | 359.83 | 36.97