## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Work Order for Preparation of DPR for new piped water supply scheme of Ghoraberia PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/RWS/Amta II | ORD/000442/2021-2022 | 243/HD | 07/02/2022 | 22/02/2022 | VOYAGER | 4.25 | 2.89 | 68.17 | 0
2 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 10.2 | 0 | 0 | 0
3 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Quotation Bill for New Service Connection at Ghoraberia W/S. Sch. PH-I |  |  | BILL/04515/2023-2024 | 556 | 21/12/2023 | 21/12/2023 | WBSEDCL | 6.69 | 0 | 0 | 0
4 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Quotation Bill for New Service Connection at Ghoraberia W/S. Sch. PH-II |  |  | BILL/04516/2023-2024 | 555 | 21/12/2023 | 21/12/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
5 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghoraberia water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer5 | ORD/000141/2022-2023 | 3509/ED | 30/12/2022 | 30/03/2023 | NUPUR CHANDRA HALDER | 21.45 | 21.3 | 99.28 | 80
6 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ghoraberia PWSS of Amta - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta2,JE/RWS/Amta II | ORD/000744/2022-2023 | 662/HD | 17/02/2023 | 19/03/2023 | LOKENATH ENTERPRISES | 28.39 | 24.13 | 85 | 100
7 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Display Board at different PWSS at Amta-I Amta-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000646/2023-2024 | 3221/AE/USD | 12/03/2024 | 11/04/2024 | ABONTICA ENTERPRISE | 4.26 | 4.26 | 100 | 100
8 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 3.7 | 0 | 0 | 0
9 | HOWRAH | Amta-II | Howrah Division | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown & 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1707 nos) for Ghoraberia PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/BLK/amta2 | ORD/000114/2023-2024 | 2698/HD | 24/07/2023 | 14/05/2026 | SUJATA CONSTRUCTION | 435.07 | 119.01 | 27.35 | 52
10 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Making of T.W. Foundation at Ghoberia water supply scheme, P.H No.- I, Dist-Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/002048/2024-2025 | 3976/HMSD | 21/08/2024 | 28/08/2024 | NUPUR CHANDRA HALDER | 0.97 | 0 | 0 | 0
11 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Additional works for Making of T.W. Foundation at Ghoraberia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/002059/2024-2025 | 5014/HMSD | 30/08/2024 | 06/09/2024 | NUPUR CHANDRA HALDER | 0.68 | 0 | 0 | 0
12 | HOWRAH | Amta-II | Electrical | Ground water based water supply scheme for Ghoraberia PWSS under Howrah Division, Block Amta-II District Howrah. | SM/11720 | New | Making of T.W. Foundation at Ghoraberia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/002060/2024-2025 | 5015/HMSD | 30/08/2024 | 06/09/2024 | NUPUR CHANDRA HALDER | 0.94 | 0 | 0 | 0
Total | [13 empty] | 520.83 | 171.59 | 32.95