## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Baniara PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000228/2022-2023 | 81/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.86 | 3.86 | 100 | 100
2 | HOWRAH | Domjur | Howrah Division | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 28.1 | 0 | 0 | 0
3 | HOWRAH | Domjur | Electrical | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Quotation Bill for New Service Connection at Baniyara W/S. Sch. TW-I & II |  |  | BILL/03760/2023-2024 | 256,257 | 05/09/2023 | 05/09/2023 | WBSEDCL | 23.59 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Quotation Bill for New Service Connection at Baniyara W/S. Sch. TW-I |  |  | BILL/04128/2023-2024 | 383 | 25/10/2023 | 25/10/2023 | WBSEDCL | 3.52 | 0 | 0 | 0
5 | HOWRAH | Domjur | Electrical | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Quotation Bill for for New Service Connection at Baniyara Porel W/S. Sch. TW-I |  |  | BILL/04315/2023-2024 | 429 | 17/11/2023 | 17/11/2023 | WBSEDCL | 0.73 | 0 | 0 | 0
6 | HOWRAH | Domjur | Howrah Division | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Baniara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/BLK/DOM/HOW,je1_iu | ORD/000659/2022-2023 | 170/HD | 13/01/2023 | 04/10/2024 | ACME CONSTRUCTION | 38.56 | 28.8 | 74.7 | 60
7 | HOWRAH | Domjur | Howrah Division | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 13.68 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Quotation money deposition for new service connection at Baniara w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008236708 Reference ID- 106843119 SM Code- 11722 |  |  | BILL/02596/2024-2025 | 632 | 18/12/2024 | 18/12/2024 | WBSEDCL | 19.17 | 0 | 0 | 0
9 | HOWRAH | Domjur | Howrah Division | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Work Order for Construction of Pump House, Boundary Wall,450 cum Capacity of 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Rising Main, Laying Distribution Pipeline & Providing FHTC (2221 nos) For Augmentation of Baniara PWSS at Domjur Block under Howrah Sadar sub Division of Howrah Division , P. H. E. DTE. | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000588/2022-2023 | 2630/HD | 08/12/2022 | 22/11/2025 | UNIQUE AGENCY | 563.14 | 307.41 | 54.59 | 50
10 | HOWRAH | Domjur | Electrical | Baniara PWSS with provision of FHTC connection | SM/11722 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniara water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000079/2023-2024 | 1996/ED | 19/05/2023 | 01/08/2026 | SANKAR PRASAD DUTTA & CO. | 35.9 | 22.74 | 63.34 | 60
Total | [13 empty] | 730.25 | 362.82 | 49.68