## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Preparation of DPR with Route Survey for new piped water supply scheme of Banharishpur PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000518/2022-2023 | 1929/HD | 19/09/2022 | 19/10/2022 | STEELCONC AND ASSOCIATES | 2.91 | 2.91 | 100 | 0
2 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 33.65 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Quotation Bill for New Service Connection at Banharishpur W/S. Sch. |  |  | BILL/02466/2023-2024 | 148 | 28/07/2023 | 28/07/2023 | WBSEDCL | 6.77 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Work Order for Construction Of 500 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work and Laying Distribution Pipeline (From Node Point-1-R1 to Node Point- 10-11)with Providing FHTC (Functional Household Tap Connection) for Augmentation of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000538/2022-2023 | 2420/HD | 23/11/2022 | 11/05/2025 | COSMO ENTERPRISE | 227.02 | 82 | 36.12 | 30
5 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Work Order for Laying of Distribution Pipeline with Functional Household Tap Connection (FHTC) of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.(Part-C) From Node Point-22-31 to Node Point- 64-65. | AE/SADAR | je_how_rws_jagat | ORD/000537/2022-2023 | 2419/HD | 23/11/2022 | 07/01/2023 | MANAS CHATTERJEE | 129.55 | 60.91 | 47.01 | 80
6 | HOWRAH |  | Electrical | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Banharishpur water supply scheme, T.W. No. III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000283/2022-2023 | 933/ED | 22/02/2023 | 23/05/2023 | A.G. ENTERPRISE | 21.49 | 10.4 | 48.4 | 50
7 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Work Order for Construction of 2 nos (5.40Mx 3.60M) Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 2nos T/well sites of Banharishpur PWSS at Panchla Block of Howrah District under Howrah Division, PHE Dte.. | AE/SADAR | je_how_rws_jagat | ORD/000075/2023-2024 | 1773/HD | 27/04/2023 | 26/06/2023 | ADRIJA ENTERPRISE | 13.25 | 6.63 | 50 | 50
8 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Laying of additional distribution pipe line adjoining to 2nd tubewell site and allied works at Banharishpur PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000631/2023-2024 | 1217/HD | 11/03/2024 | 25/04/2024 | JHARNA ENTERPRISE | 27.15 | 14.14 | 52.08 | 20
9 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Additional laying distribution pipe line and allied works at Banharishpur PWSS under Shyamchak mouza at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000594/2023-2024 | 998/HD | 01/03/2024 | 15/05/2024 | S RAHA ENTERPRISE | 74.68 | 44.35 | 59.39 | 60
10 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 27.73 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Quotation money deposition for new service connection at Banharishpur pwss, P.H No.-I Dist-Howrah under ED PHED. App. No.-1007561303 Ref. ID.- 106491239 SM/11723 |  |  | BILL/06247/2023-2024 | 851 | 07/03/2024 | 07/03/2024 | WBSEDCL | 25.8 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jaynagar PWSS(2 nos) & Banharishpur PWSS(2 nos) of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000800/2022-2023 | 1000/HD | 13/03/2023 | 14/11/2025 | PRANTIK DRILLING AGENCY | 68.83 | 15.17 | 22.04 | 25
13 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 12.48 | 0.02 | 0.2 | 62
14 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Additional Pipe distribution system, Construction of R.C.C Slab Culvert, construction of approach Road with land development & boundary wall at 2nd T/W Site at Banharishpur piped water supply scheme under Banharishpur Mouza Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000656/2023-2024 | 1245/HD | 12/03/2024 | 06/05/2025 | COSMO ENTERPRISE | 51.65 | 17.1 | 33.1 | 25
15 | HOWRAH |  | Howrah Division | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | SM/11723 | Augmentation | Work Order for Laying Distribution Pipe Lines With Functional Household Tap Connection(FHTC) for Augmentation of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, PHE Dte.(Part-B) From Node Point-8-22 to Node Point-54-61. | AE/SADAR | je_how_rws_jagat | ORD/000508/2022-2023 | 2257/HD | 04/11/2022 | 27/01/2025 | MITHU BUILDERS | 129.62 | 101.3 | 78.15 | 100
Total | [13 empty] | 852.58 | 354.93 | 41.63