## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR | JE/RWS/Jagatballavpur | ORD/000076/2022-2023 | 1019/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 100 | 0
2 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 4.58 | 0 | 0 | 0
3 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. |  |  | VCH/000776/2022-2023 |  | 20/10/2022 | 20/10/2022 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0 | 0
4 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shyampur PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000666/2022-2023 | 177/HD | 13/01/2023 | 27/02/2023 | MUNSHI ENTERPRISE | 25.96 | 25.02 | 96.35 | 100
5 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, Zone-I, P.H. No. II (Replaced tubewell), District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4,Junior Engineer5 | ORD/001159/2022-2023 | 2099/HMSD | 24/11/2022 | 24/12/2022 | D. K. ELECTRIC | 4.3 | 4.3 | 100 | 0
6 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Quotation Bill for New Service Connection at Shyampur PH-I |  |  | BILL/00907/2022-2023 | 188 | 13/03/2023 | 13/03/2023 | WBSEDCL | 2.57 | 0 | 0 | 0
7 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Quotation Bill for New Service Connection at Shyampur W/S. Sch. PH-II |  |  | BILL/01891/2022-2023 | 229 | 29/03/2023 | 29/03/2023 | WBSEDCL | 2.69 | 0 | 0 | 0
8 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) At 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | AE/SADAR |  | ORD/000587/2022-2023 | 2617/HD | 08/12/2022 | 06/02/2023 | MONIRUL ISLAM | 6.14 | 5.78 | 94.15 | 100
9 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-9- J-10 to Section J-140 - J-141 (Part-2) | AE/SADAR | JE/RWS/Jagatballavpur,je_how_rws_jagat | ORD/000505/2022-2023 | 2260/HD | 04/11/2022 | 19/12/2022 | BUILT INDIA | 18.8 | 17.8 | 94.64 | 100
10 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-16- J-17 to Section J-157-J-158 (Part-1) | AE/SADAR |  | ORD/000590/2022-2023 | 2604/HD | 07/12/2022 | 21/01/2023 | MA DURGA ENTERPRISE | 15.61 | 15.42 | 98.75 | 50
11 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) at 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | AE/SADAR |  | ORD/000586/2022-2023 | 2603/HD | 07/12/2022 | 05/02/2023 | NAG ENTERPRISE | 6.17 | 5.8 | 94.08 | 100
12 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work order for Laying Additional DI Pipe line LDS Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000067/2023-2024 | 1928/HD | 10/05/2023 | 09/07/2023 | MONIRUL ISLAM | 4.11 | 4.03 | 98 | 100
13 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Laying Rising Main Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000068/2023-2024 | 1929/HD | 10/05/2023 | 09/07/2023 | KUNAL BANERJEE | 3.96 | 3.79 | 95.83 | 100
14 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001364/2022-2023 | 3522/ED | 30/12/2022 | 30/03/2023 | S P ENTERPRISE | 20.28 | 20.27 | 99.95 | 11
15 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Construction of 2 nos. Boundary Wall at pump house of Shyampur PWSS at J.B Pur Block of Howrah District under Howrah Division, P. H. E. Dte. Size-(25.00 m x 20.00 m) | AE/SADAR | JE Sadar | ORD/000306/2023-2024 | 4318/HD | 01/12/2023 | 30/01/2024 | ADRIJA ENTERPRISE | 15.43 | 15.39 | 99.75 | 100
16 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.From Section R-1 - J-1 to Section J-134 - J-136 (Part-3) | AE/SADAR | JE/RWS/Jagatballavpur,je_how_rws_jagat | ORD/000504/2022-2023 | 2259/HD | 04/11/2022 | 19/12/2022 | AQUATECH ENGINEERS | 30.98 | 27.46 | 88.61 | 100
17 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Laying of additional distribution pipe line for providing FHTC at Shyampur PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE.Dte. | AE/SADAR | je_how_rws_jagat | ORD/000400/2024-2025 | 1355/HSSD | 27/12/2024 | 10/02/2025 | MA DURGA ENTERPRISE | 1.92 | 0 | 0 | 100
18 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Construction of approach road and land Development at 1st tubewell site for Shyampur PWSS at J.B.PUR Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000107/2025-2026 | 3086/HD | 08/07/2025 | 07/08/2025 | ADRIJA ENTERPRISE | 5.55 | 0 | 0 | 0
Total | [13 empty] | 174.11 | 147.58 | 84.76