## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR | JE/RWS/Jagatballavpur | ORD/000076/2022-2023 | 1019/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 100 | 0
2 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 4.58 | 0 | 0 | 0
3 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. |  |  | VCH/000776/2022-2023 |  | 20/10/2022 | 20/10/2022 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0 | 0
4 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shyampur PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000666/2022-2023 | 177/HD | 13/01/2023 | 27/02/2023 | MUNSHI ENTERPRISE | 25.96 | 25.02 | 96.35 | 100
5 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, Zone-I, P.H. No. II (Replaced tubewell), District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4,Junior Engineer5 | ORD/001159/2022-2023 | 2099/HMSD | 24/11/2022 | 24/12/2022 | D. K. ELECTRIC | 4.3 | 4.3 | 100 | 0
6 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Quotation Bill for New Service Connection at Shyampur PH-I |  |  | BILL/00907/2022-2023 | 188 | 13/03/2023 | 13/03/2023 | WBSEDCL | 2.57 | 0 | 0 | 0
7 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Quotation Bill for New Service Connection at Shyampur W/S. Sch. PH-II |  |  | BILL/01891/2022-2023 | 229 | 29/03/2023 | 29/03/2023 | WBSEDCL | 2.69 | 0 | 0 | 0
8 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) At 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | AE/SADAR |  | ORD/000587/2022-2023 | 2617/HD | 08/12/2022 | 06/02/2023 | MONIRUL ISLAM | 6.14 | 5.78 | 94.15 | 100
9 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-9- J-10 to Section J-140 - J-141 (Part-2) | AE/SADAR | JE/RWS/Jagatballavpur,je_how_rws_jagat | ORD/000505/2022-2023 | 2260/HD | 04/11/2022 | 19/12/2022 | BUILT INDIA | 18.8 | 17.8 | 94.64 | 100
10 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-16- J-17 to Section J-157-J-158 (Part-1) | AE/SADAR |  | ORD/000590/2022-2023 | 2604/HD | 07/12/2022 | 21/01/2023 | MA DURGA ENTERPRISE | 15.61 | 15.42 | 98.75 | 50
11 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) at 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | AE/SADAR |  | ORD/000586/2022-2023 | 2603/HD | 07/12/2022 | 05/02/2023 | NAG ENTERPRISE | 6.17 | 5.8 | 94.08 | 100
12 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work order for Laying Additional DI Pipe line LDS Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000067/2023-2024 | 1928/HD | 10/05/2023 | 09/07/2023 | MONIRUL ISLAM | 4.11 | 4.03 | 98 | 100
13 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work Order for Laying Rising Main Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000068/2023-2024 | 1929/HD | 10/05/2023 | 09/07/2023 | KUNAL BANERJEE | 3.96 | 3.79 | 95.83 | 100
14 | HOWRAH | Jagatballavpur | Electrical | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001364/2022-2023 | 3522/ED | 30/12/2022 | 30/03/2023 | S P ENTERPRISE | 20.28 | 20.27 | 99.95 | 11
15 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Construction of 2 nos. Boundary Wall at pump house of Shyampur PWSS at J.B Pur Block of Howrah District under Howrah Division, P. H. E. Dte. Size-(25.00 m x 20.00 m) | AE/SADAR | JE Sadar | ORD/000306/2023-2024 | 4318/HD | 01/12/2023 | 30/01/2024 | ADRIJA ENTERPRISE | 15.43 | 15.39 | 99.75 | 100
16 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Work order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.From Section R-1 - J-1 to Section J-134 - J-136 (Part-3) | AE/SADAR | JE/RWS/Jagatballavpur,je_how_rws_jagat | ORD/000504/2022-2023 | 2259/HD | 04/11/2022 | 19/12/2022 | AQUATECH ENGINEERS | 30.98 | 27.46 | 88.61 | 100
17 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Construction of approach road and land Development at 1st tubewell site for Shyampur PWSS at J.B.PUR Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000107/2025-2026 | 3086/HD | 08/07/2025 | 07/08/2025 | ADRIJA ENTERPRISE | 5.55 | 0 | 0 | 0
18 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Laying distribution pipe line (DI) between node point J34 to J46 of Shyampur PWSS at Jagatballavpur Block of Howrah District under Howrah sadar sub division of Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000423/2024-2025 | 1186/HSSD | 20/11/2024 | 19/01/2025 | MANIRUL ISLAM | 0.96 | 0 | 0 | 100
19 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Laying of additional distribution pipe line for providing FHTC at Shyampur PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE.Dte. | AE/SADAR | je_how_rws_jagat | ORD/000400/2024-2025 | 1355/HSSD | 27/12/2024 | 10/02/2025 | MA DURGA ENTERPRISE | 1.92 | 0 | 0 | 100
20 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Reconnection of FHTC and C.C.Road restoration for Shyampur PWSS at J.B.PUR Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000644/2024-2025 | 1177/HD | 03/03/2025 | 02/05/2025 | M/S SUPROVAT GHOSH | 7.19 | 0 | 0 | 100
21 | HOWRAH | Jagatballavpur | Howrah Division | Shyampur Piped Water Supply Scheme, Block- Jagatballavpur, Dist- Howrah. | SM/11790 | New | Supplying,fitting,fixing and erecting of Display Board at Shekrahati PWSS [SM/09586], Nimabalia PWSS [SM/13770], Shyampur PWSS [SM/11790] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000983/2024-2025 | 231-A/HSSD | 28/02/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
Total | [13 empty] | 183.12 | 147.58 | 80.59