## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Work Order for Preparation of DPR for new piped water supply scheme of Nawapara PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000444/2021-2022 | 245/HD | 07/02/2022 | 22/02/2022 | VOYAGER | 3.2 | 0 | 0 | 0
2 | HOWRAH | Amta-II | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawapara water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer6 | ORD/000167/2022-2023 | 3517/ED | 30/12/2022 | 30/03/2023 | T S CONSTRUCTION | 22.49 | 0 | 0 | 80
3 | HOWRAH | Amta-II | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Uttar Khariop water supply scheme, T.W. No. III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/000095/2023-2024 | 2076/ED | 31/05/2023 | 29/08/2023 | D. K. ELECTRIC | 10.72 | 0 | 0 | 100
4 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta2,JE/USD | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 25/11/2023 | PRANTIK DRILLING AGENCY | 77.89 | 0 | 0 | 100
5 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 10.04 | 0 | 0 | 0
6 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1286/HD | 13/03/2024 | 13/03/2024 | Resource Division | 22.35 | 0 | 0 | 0
7 | HOWRAH | Amta-II | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Quotation Bill for New Service Connection at Nowpara W/S. Sch. PH-II |  |  | BILL/04628/2023-2024 | 617 | 08/01/2024 | 08/01/2024 | WBSEDCL | 4.22 | 0 | 0 | 0
8 | HOWRAH | Amta-II | Electrical | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Quotation Bill for New Service Connection at Nowpara W/S. Sch. PH-I |  |  | BILL/04629/2023-2024 | 618 | 08/01/2024 | 08/01/2024 | WBSEDCL | 7.8 | 0 | 0 | 0
9 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation & foundation design, Laying Distribution Pipeline & Providing FHTC (3243 nos) for Nawapara Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000176/2023-2024 | 2947/HD | 14/08/2023 | 15/05/2026 | ORIENT CONSTRUCTION | 675.07 | 0 | 0 | 60
10 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Construction of boundary wall & Land Development at HW Site Nawpara PWSS scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/11793) | AE/Ulu |  | ORD/000783/2024-2025 | 1510/HD | 21/03/2025 | 20/05/2025 | APEX ENGINEERING | 21.55 | 0 | 0 | 0
11 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Construction of boundary wall & Land Development at 2nd TW Site Nawpara PWSS scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/11793) | AE/Ulu | JE/USD | ORD/000546/2024-2025 | 1072/HD | 27/02/2025 | 10/10/2025 | M/S KANIKA ROY ENTERPRISE | 12.37 | 0 | 0 | 80
12 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water supply Scheme for Nawapara PWSS, under Howrah Division, Block Amta-II, District Howrah. | SM/11793 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ | je_blk_ballyjag_how | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 01/11/2025 | TECH VISION | 21.25 | 0 | 0 | 0
Total | [13 empty] | 888.96 | 0 | 0