## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Preparation of DPR for new piped water supply scheme of Khorda Etarai PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000452/2021-2022 | 253/HD | 07/02/2022 | 22/02/2022 | APEX ENGINEERING | 2.91 | 2.61 | 89.48 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000628/2022-2023 | 2809/HD | 21/12/2022 | 19/02/2023 | SR TRADING CORPORATION | 8.5 | 7.77 | 91.4 | 100
3 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khordah Etarai PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000560/2022-2023 | 2490/HD | 30/11/2022 | 14/01/2023 | DEV DAS SHAW | 27.37 | 22.53 | 82.31 | 100
4 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 2.18 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 4.52 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 2716/HD | 25/07/2023 | 25/07/2023 | Resource Division | 13.78 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Electrical | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Quotation bill for new service connection of Kharda Itarai PWSS, P.H-II |  |  | BILL/00721/2023-2024 | 17 | 02/05/2023 | 02/05/2023 | WBSEDCL | 7.81 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Electrical | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | QUOTATION FOR NEW SERVICE CONNECTION OF KHORDA ETARAI W/S SCHEME PH NO-I, ELECTRICAL DIVISION, PHE DTE |  |  | BILL/00751/2023-2024 | 39 | 15/05/2023 | 15/05/2023 | WBSEDCL | 7.36 | 0 | 0 | 0
9 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Raising main & Inter Connection with both tube wells of Khodra Etarai PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Uluberia I | ORD/000343/2023-2024 | 4636/HD | 21/12/2023 | 05/01/2024 | UNIVERSAL CONSTRUCTION | 6.87 | 5.33 | 77.61 | 100
10 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000626/2022-2023 | 2806/HD | 21/12/2022 | 19/02/2023 | JAHANGIR ALAM | 8.42 | 7.54 | 89.59 | 98
11 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 28/HD | 03/01/2024 | 03/01/2024 | Resource Division | 0.87 | 0 | 0 | 0
12 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Construction of 100 cum Capacity 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (733 nos) for KHORDA ETARAI PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000618/2022-2023 | 2784/HD | 20/12/2022 | 07/06/2025 | AJAY MONDAL | 191.45 | 95.65 | 49.96 | 55
13 | HOWRAH | Udaynarayanpur | Electrical | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khorda Etarai water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000137/2022-2023 | 3513/ED | 30/12/2022 | 01/09/2024 | MAHAMAYA ENTERPRISE | 20.36 | 19.58 | 96.2 | 90
Total | [13 empty] | 302.41 | 161.02 | 53.25