## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Preparation of DPR for new piped water supply scheme of Khorda Etarai PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000452/2021-2022 | 253/HD | 07/02/2022 | 22/02/2022 | APEX ENGINEERING | 2.91 | 2.61 | 89.48 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000628/2022-2023 | 2809/HD | 21/12/2022 | 19/02/2023 | SR TRADING CORPORATION | 8.5 | 7.77 | 91.4 | 100
3 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khordah Etarai PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000560/2022-2023 | 2490/HD | 30/11/2022 | 14/01/2023 | DEV DAS SHAW | 27.37 | 22.53 | 82.31 | 100
4 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 2.18 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 4.52 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 2716/HD | 25/07/2023 | 25/07/2023 | Resource Division | 13.78 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Electrical | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Quotation bill for new service connection of Kharda Itarai PWSS, P.H-II |  |  | BILL/00721/2023-2024 | 17 | 02/05/2023 | 02/05/2023 | WBSEDCL | 7.81 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Electrical | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | QUOTATION FOR NEW SERVICE CONNECTION OF KHORDA ETARAI W/S SCHEME PH NO-I, ELECTRICAL DIVISION, PHE DTE |  |  | BILL/00751/2023-2024 | 39 | 15/05/2023 | 15/05/2023 | WBSEDCL | 7.36 | 0 | 0 | 0
9 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Raising main & Inter Connection with both tube wells of Khodra Etarai PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Uluberia I | ORD/000343/2023-2024 | 4636/HD | 21/12/2023 | 05/01/2024 | UNIVERSAL CONSTRUCTION | 6.87 | 5.33 | 77.61 | 100
10 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000626/2022-2023 | 2806/HD | 21/12/2022 | 19/02/2023 | JAHANGIR ALAM | 8.42 | 7.54 | 89.59 | 98
11 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 28/HD | 03/01/2024 | 03/01/2024 | Resource Division | 0.87 | 0 | 0 | 0
12 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Work Order for Construction of 100 cum Capacity 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (733 nos) for KHORDA ETARAI PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000618/2022-2023 | 2784/HD | 20/12/2022 | 07/06/2025 | AJAY MONDAL | 191.45 | 95.65 | 49.96 | 55
13 | HOWRAH | Udaynarayanpur | Electrical | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khorda Etarai water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000137/2022-2023 | 3513/ED | 30/12/2022 | 01/09/2024 | MAHAMAYA ENTERPRISE | 20.36 | 19.58 | 96.2 | 90
14 | HOWRAH | Udaynarayanpur | Howrah Division | Khorda Etarai Piped Water Supply Scheme | SM/11892 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 13/04/2026 | HORIZEN | 13.59 | 1.78 | 13.1 | 70
Total | [13 empty] | 316 | 162.8 | 51.52