## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Khasmara (Zone-III) PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000205/2022-2023 | 78/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.42 | 3.42 | 100 | 0
2 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 130.95 | 0 | 0 | 0
3 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation Bill for New Service Connection at Khasmara W/S. Sch. PWSS-II |  |  | BILL/04130/2023-2024 | 377 | 25/10/2023 | 25/10/2023 | WBSEDCL | 15.25 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation Bill for New Service Connection at Khasmara W/S. Sch. Howrah |  |  | BILL/02723/2023-2024 | 167 | 04/08/2023 | 04/08/2023 | WBSEDCL | 0.22 | 0 | 0 | 0
5 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation Bill for New Service Connection at Domjur, Khasmara W/S. Sch. Z-III |  |  | BILL/00841/2023-2024 | 65 | 08/06/2023 | 08/06/2023 | WBSEDCL | 2.34 | 0 | 0 | 0
6 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Deposition of additional quotation money for domjur zone-III ( KHASMARA) w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. |  |  | BILL/00967/2023-2024 |  | 07/06/2023 | 07/06/2023 | WBSEDCL | 2.34 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation money deposit for Domjur (Zone-III) Khasmara W/S ,P.H No.-I |  |  | BILL/00732/2023-2024 | 21 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.69 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khasmara Domjur (Zone-III) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000155/2022-2023 | 3512/ED | 30/12/2022 | 30/03/2023 | H.K.DAS & CO. | 34.31 | 24.52 | 71.49 | 65
9 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (ZoneIII) Khasmara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000663/2022-2023 | 174/HD | 13/01/2023 | 27/02/2023 | BALAJI UDDYOG | 38.37 | 36.78 | 95.84 | 100
10 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Concrete Approach Road at 1st Tubewell Site at Domjur (Zone-III) Khashmora PWSS under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000020/2024-2025 | 2725/HD | 11/06/2024 | 26/07/2024 | SUJATA CONSTRUCTION | 9.63 | 9.57 | 99.44 | 100
11 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 14.79 | 0 | 0 | 0
12 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation money deposition for new service connection at Khasmara (Domjur Zone-III) Pwss P.H No-III , Dist-Howrah under ED, PHED. |  |  | BILL/06055/2023-2024 | 752 | 16/02/2024 | 16/02/2024 | WBSEDCL | 12.75 | 0 | 0 | 0
13 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Work Order for 3 nos Construction of Pump House (5.40m x 3.60 m) at 1st , 2nd &3rd Tube Well Site ,Construction of Boundary Wall at 1st Tube Well Site,Construction of 2 nos Boundary Wall at 2nd & 3rd Tube Well Site,Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Domjur (Zone-III) Khasmara PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000029/2023-2024 | 1698/HD | 21/04/2023 | 01/11/2025 | SUJATA CONSTRUCTION | 452.67 | 313.36 | 69.23 | 45
14 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line From Node No. 149 to 292 of Domjur (Zome-3) Khasmora PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000097/2025-2026 | 2942/HD | 25/06/2025 | 23/10/2025 | SUJATA CONSTRUCTION | 59.8 | 0 | 0 | 0
15 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Pipe Carrying Structure for Crossing of Keto Pol at Khasmora PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR |  | ORD/000482/2024-2025 | 1014/HD | 21/02/2025 | 22/04/2025 | GUPTA ENTERPRISE | 37.95 | 0 | 0 | 0
16 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Domjur Block) | AE HQ |  | ORD/000230/2025-2026 | 4128/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
17 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Khasmora (Zone-3) PWSS at 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000021/2024-2025 | 2726/HD | 11/06/2024 | 02/06/2025 | SUJATA CONSTRUCTION | 11.55 | 0 | 0 | 100
18 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000111/2024-2025 | 3730/HD | 29/08/2024 | 28/09/2024 | HORIZEN | 4.93 | 0 | 0 | 100
Total | [13 empty] | 836.74 | 387.66 | 46.33