## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Khasmara (Zone-III) PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000205/2022-2023 | 78/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.42 | 0 | 0 | 0
2 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 130.95 | 0 | 0 | 0
3 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation Bill for New Service Connection at Khasmara W/S. Sch. PWSS-II |  |  | BILL/04130/2023-2024 | 377 | 25/10/2023 | 25/10/2023 | WBSEDCL | 15.25 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation Bill for New Service Connection at Khasmara W/S. Sch. Howrah |  |  | BILL/02723/2023-2024 | 167 | 04/08/2023 | 04/08/2023 | WBSEDCL | 0.22 | 0 | 0 | 0
5 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation Bill for New Service Connection at Domjur, Khasmara W/S. Sch. Z-III |  |  | BILL/00841/2023-2024 | 65 | 08/06/2023 | 08/06/2023 | WBSEDCL | 2.34 | 0 | 0 | 0
6 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Deposition of additional quotation money for domjur zone-III ( KHASMARA) w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. |  |  | BILL/00967/2023-2024 |  | 07/06/2023 | 07/06/2023 | WBSEDCL | 2.34 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation money deposit for Domjur (Zone-III) Khasmara W/S ,P.H No.-I |  |  | BILL/00732/2023-2024 | 21 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.69 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khasmara Domjur (Zone-III) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000155/2022-2023 | 3512/ED | 30/12/2022 | 30/03/2023 | H.K.DAS & CO. | 34.31 | 0 | 0 | 65
9 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (ZoneIII) Khasmara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000663/2022-2023 | 174/HD | 13/01/2023 | 27/02/2023 | BALAJI UDDYOG | 38.37 | 0 | 0 | 100
10 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Concrete Approach Road at 1st Tubewell Site at Domjur (Zone-III) Khashmora PWSS under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000020/2024-2025 | 2725/HD | 11/06/2024 | 26/07/2024 | SUJATA CONSTRUCTION | 9.63 | 0 | 0 | 100
11 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 14.79 | 0 | 0 | 0
12 | HOWRAH | Domjur | Electrical | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Quotation money deposition for new service connection at Khasmara (Domjur Zone-III) Pwss P.H No-III , Dist-Howrah under ED, PHED. |  |  | BILL/06055/2023-2024 | 752 | 16/02/2024 | 16/02/2024 | WBSEDCL | 12.75 | 0 | 0 | 0
13 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Work Order for 3 nos Construction of Pump House (5.40m x 3.60 m) at 1st , 2nd &3rd Tube Well Site ,Construction of Boundary Wall at 1st Tube Well Site,Construction of 2 nos Boundary Wall at 2nd & 3rd Tube Well Site,Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Domjur (Zone-III) Khasmara PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000029/2023-2024 | 1698/HD | 21/04/2023 | 01/11/2025 | SUJATA CONSTRUCTION | 452.67 | 0 | 0 | 45
14 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line From Node No. 149 to 292 of Domjur (Zome-3) Khasmora PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000097/2025-2026 | 2942/HD | 25/06/2025 | 23/10/2025 | SUJATA CONSTRUCTION | 59.8 | 0 | 0 | 0
15 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Pipe Carrying Structure for Crossing of Keto Pol at Khasmora PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR |  | ORD/000482/2024-2025 | 1014/HD | 21/02/2025 | 22/04/2025 | GUPTA ENTERPRISE | 37.95 | 0 | 0 | 0
16 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-III) Khasmara PWSS with provision of FHTC connection Block-Domjur | SM/11893 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Domjur Block) | AE HQ |  | ORD/000230/2025-2026 | 4128/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
Total | [13 empty] | 820.26 | 0 | 0