## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-I) PWSS (Mouza-Mahisgote, Chak Mahisjol, Chal Hari, Mahisnala, Nanakundu & Chak Kadamtala) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000236/2022-2023 | 89/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.19 | 3.19 | 100 | 0
2 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 50.64 | 0 | 0 | 0
3 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Quotation Bill for New Service Connection at Mahishnala W/S. Sch. PWSS-II |  |  | BILL/04129/2023-2024 | 379 | 25/10/2023 | 25/10/2023 | WBSEDCL | 9.03 | 0 | 0 | 0
4 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000001/2023-2024 | 1530/HD | 04/04/2023 | 19/05/2023 | BALAJI UDDYOG | 89.53 | 61.84 | 69.07 | 70
5 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 12.09 | 0 | 0 | 0
6 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Quotation money deposition for new service connection at Mohisnala w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007840878 Reference ID- 106627061 SM Code- 11894 |  |  | BILL/00832/2024-2025 | 231 | 20/06/2024 | 20/06/2024 | WBSEDCL | 13.93 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Quotation money deposition for new service connection at Mahisnala (Domjur Zone-I) Pwss P.H No-III , Dist-Howrah under ED, PHED. |  |  | BILL/06056/2023-2024 | 757 | 16/02/2024 | 16/02/2024 | WBSEDCL | 7.55 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-04G-2822 Bill No : 0240 Bill Date : 31/05/2024 |  |  | BILL/00833/2024-2025 | 241 | 20/06/2024 | 20/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
9 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisnala Domjur (Zone-I) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000151/2022-2023 | 3515/ED | 30/12/2022 | 15/09/2025 | DAS ENTERPRISE | 34.26 | 0 | 0 | 75
10 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Emergency Restoration of CI/DI Pipeline along with damaged at Node No. 22 to 270 main road due to laying of pipe line of Domjur (Zone-1) Mahishnala PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000109/2025-2026 | 3130/HD | 14/07/2025 | 28/08/2025 | MONDAL ENTERPISE | 42.03 | 0 | 0 | 0
11 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Pipe Carrying Structure for Crossing at Node No. 104 to 109 of Mahishnala PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR |  | ORD/000424/2024-2025 | 867/HD | 10/02/2025 | 11/04/2025 | GUPTA ENTERPRISE | 36.93 | 0 | 0 | 0
12 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Mahishnala (Zone-1) PWSS at 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000626/2023-2024 | 1135/HD | 06/03/2024 | 09/09/2024 | KALIDAS ENTERPRISE | 12.66 | 7.72 | 60.96 | 50
Total | [13 empty] | 312.08 | 72.75 | 23.31