## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-I) PWSS (Mouza-Mahisgote, Chak Mahisjol, Chal Hari, Mahisnala, Nanakundu & Chak Kadamtala) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000236/2022-2023 | 89/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.19 | 0 | 0 | 0
2 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 50.64 | 0 | 0 | 0
3 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Quotation Bill for New Service Connection at Mahishnala W/S. Sch. PWSS-II |  |  | BILL/04129/2023-2024 | 379 | 25/10/2023 | 25/10/2023 | WBSEDCL | 9.03 | 0 | 0 | 0
4 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000001/2023-2024 | 1530/HD | 04/04/2023 | 19/05/2023 | BALAJI UDDYOG | 89.53 | 0 | 0 | 70
5 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 12.09 | 0 | 0 | 0
6 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Quotation money deposition for new service connection at Mohisnala w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007840878 Reference ID- 106627061 SM Code- 11894 |  |  | BILL/00832/2024-2025 | 231 | 20/06/2024 | 20/06/2024 | WBSEDCL | 13.93 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Quotation money deposition for new service connection at Mahisnala (Domjur Zone-I) Pwss P.H No-III , Dist-Howrah under ED, PHED. |  |  | BILL/06056/2023-2024 | 757 | 16/02/2024 | 16/02/2024 | WBSEDCL | 7.55 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-04G-2822 Bill No : 0240 Bill Date : 31/05/2024 |  |  | BILL/00833/2024-2025 | 241 | 20/06/2024 | 20/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
9 | HOWRAH | Domjur | Electrical | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisnala Domjur (Zone-I) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000151/2022-2023 | 3515/ED | 30/12/2022 | 15/09/2025 | DAS ENTERPRISE | 34.26 | 0 | 0 | 75
10 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | 3 Nos Construction of Pump House (5.40m x 3.60 m), 3 nos Construction of Boundary Wall at 1st, 2nd &3rd Tube Well Sites, Construction of 350 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-I) Mahisnala PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000127/2023-2024 | 2622/HD | 17/07/2023 | 06/07/2026 | MONDAL PRECISION PVT. LTD. | 411.41 | 0 | 0 | 40
11 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 14/12/2025 | TECH VISION | 8.36 | 0 | 0 | 79
12 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Emergency Restoration of CI/DI Pipeline along with damaged at Node No. 22 to 270 main road due to laying of pipe line of Domjur (Zone-1) Mahishnala PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000109/2025-2026 | 3130/HD | 14/07/2025 | 28/08/2025 | MONDAL ENTERPISE | 42.03 | 0 | 0 | 0
13 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Pipe Carrying Structure for Crossing at Node No. 104 to 109 of Mahishnala PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR |  | ORD/000424/2024-2025 | 867/HD | 10/02/2025 | 11/04/2025 | GUPTA ENTERPRISE | 36.93 | 0 | 0 | 0
14 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-I) Mahisnala PWSS with provision of FHTC connection Block-Domjur | SM/11894 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Mahishnala (Zone-1) PWSS at 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000626/2023-2024 | 1135/HD | 06/03/2024 | 09/09/2024 | KALIDAS ENTERPRISE | 12.66 | 0 | 0 | 50
Total | [13 empty] | 731.84 | 0 | 0