## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Preparation of DPR for new piped water supply scheme of Khila PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000255/2022-2023 | 329/AE/USD | 16/08/2022 | 30/09/2022 | STEELCONC AND ASSOCIATES | 4.01 | 0 | 0 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 8.77 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 29.79 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 3217/HD | 05/09/2023 | 05/09/2023 | Resource Division | 38.86 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Electrical | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | QUOTATION OF NEW SERVICE CONNECTION FOR KHILA W/S SCHEME, PH NO-III |  |  | BILL/02133/2023-2024 | 124 | 20/07/2023 | 20/07/2023 | WBSEDCL | 6.1 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection(FHTC) of KHILA Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B). | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000819/2022-2023 | 1104/HD | 17/03/2023 | 27/07/2025 | JAHANGIR ALAM | 113 | 0 | 0 | 35
7 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Construction of Boundary Wall, Approach Road, Land Development and Pump house at HEAD WORK Site, 2nd Tube Well Site and 3rd Tube Well Site of KHILA Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.[SM/12270] | AE/RWS | JE/RWS/Uluberia I | ORD/000154/2024-2025 | 4130/HD | 23/09/2024 | 02/03/2026 | JAHANGIR ALAM | 102.93 | 0 | 0 | 50
8 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khila PWSS of RWS Howrah Sub-Division under Howrah Division, P. H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000558/2022-2023 | 2488/HD | 30/11/2022 | 29/01/2023 | M/S SYCHROTECH INDUSTRY | 54.33 | 0 | 0 | 100
9 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 3rd TW site Khila W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000623/2022-2023 | 2803/HD | 21/12/2022 | 19/02/2023 | MAITY CONSTRUCTIONS | 7.7 | 0 | 0 | 60
10 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | NDT of OHR of of Khila PWSSS |  |  | BILL/00328/2024-2025 | BP-2024-25-197 | 22/07/2024 | 22/07/2024 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0 | 0
11 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Acceptance cum Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of KHILA Piped Water Supply Scheme under Udaynaryanpur block under Uluberia Sub- Division, PHE Dte.(Part-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,JE Sadar | ORD/000884/2022-2023 | 1450/HD | 30/03/2023 | 23/09/2025 | M/S EL-CON | 620.6 | 0 | 0 | 50
12 | HOWRAH | Udaynarayanpur | Electrical | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khila water supply scheme, T.W. No.- I, II & III, Block: Udaynaraynpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000116/2022-2023 | 3554/ED | 30/12/2022 | 01/11/2025 | M/S P.P. ELECTRICALS | 30.54 | 0 | 0 | 50
13 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 19/03/2025 | HORIZEN | 13.59 | 0 | 0 | 60
14 | HOWRAH | Udaynarayanpur | Howrah Division | Khila Piped Water Supply Scheme with FHTC, Block Udaynarayanpur. | SM/12270 | New | Construction of 600 cum capacity 20 mtr. Staging height RCC Elevated Reservoir as per Departmental Design Drawing including Soil Investigation, Design of Pile foundation & all pipe connections for KHILA PWSS of Udaynarayanpur Block under Howrah Division, P.H.E. Dte. (SM/12270) | AE/RWS | JE/RWS/Uluberia I | ORD/000105/2025-2026 | 3083/HD | 08/07/2025 | 08/07/2026 | ABDUL HAI | 158.66 | 0 | 0 | 0
Total | [13 empty] | 1190.65 | 0 | 0