## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Preparation of DPR with Route Survey for new piped water supply scheme of Samanti PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000520/2022-2023 | 1947/HD | 20/09/2022 | 20/10/2022 | STEELCONC AND ASSOCIATES | 3.98 | 3.98 | 100 | 0
2 | HOWRAH | Panchla | Electrical | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanti water supply scheme, T.W. No.- I, II, III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000153/2022-2023 | 3520/ED | 30/12/2022 | 30/03/2023 | R.N.S. TRADING | 43.41 | 0 | 0 | 0
3 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 307.14 | 0 | 0 | 0
4 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Samanti PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000693/2022-2023 | 311/HD | 20/01/2023 | 19/02/2023 | ZEOLITE FRESH INDIA | 34.42 | 34.11 | 99.12 | 100
5 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 42.29 | 0 | 0 | 0
6 | HOWRAH | Panchla | Electrical | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Quotation money deposition for new service connection at Samanti PWSS P.H No- III , Dist-Howrah under ED PHED. Application No.-1007542321 dated- 17/02/2024 Ref. ID.- 106478203 |  |  | BILL/06164/2023-2024 | 797 | 23/02/2024 | 23/02/2024 | WBSEDCL | 3.59 | 0 | 0 | 0
7 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Work Order for Construction of Pump House, Boundary Wall,700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Rising Main , Laying Distribution Pipeline & Provinding FHTC (6865 nos) For Samanti PWSS at Panchla Block under Howrah Sadar sub Division of Howrah Division, P. H. E. DTE. | AE/SADAR | je_how_rws_jagat | ORD/000562/2022-2023 | 2500/HD | 30/11/2022 | 19/11/2025 | M/S S.S. ENTERPRISE | 789.11 | 433.49 | 54.93 | 40
8 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Additional Laying Distribution Pipeline & Adopting 2 nos Jack Pushing of 700 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 198-200 & 53-200 of LDS drawing) on Ranihati-Amta Road of Samanti PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/12562) | AE/SADAR | je_how_rws_jagat | ORD/000068/2024-2025 | 3106/HD | 08/07/2024 | 01/10/2025 | M/S S.S. ENTERPRISE | 459.55 | 228.52 | 49.73 | 65
9 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 12.48 | 5.39 | 43.17 | 62
10 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Sinking 2nos. 300 X 200 mm dia and 230 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 45m. long PVC housing pipe & 200 mm dia. 155m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Samanti PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000067/2025-2026 | 2574/HD | 02/06/2025 | 29/11/2025 | G.T.AGRO CENTRE | 36.04 | 0 | 0 | 0
Total | [13 empty] | 1732.01 | 705.5 | 40.73