## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Preparation of DPR with Route Survey for new piped water supply scheme of Samanti PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000520/2022-2023 | 1947/HD | 20/09/2022 | 20/10/2022 | STEELCONC AND ASSOCIATES | 3.98 | 3.98 | 100 | 0
2 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 307.14 | 0 | 0 | 0
3 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Samanti PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000693/2022-2023 | 311/HD | 20/01/2023 | 19/02/2023 | ZEOLITE FRESH INDIA | 34.42 | 34.11 | 99.12 | 100
4 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 42.29 | 0 | 0 | 0
5 | HOWRAH | Panchla | Electrical | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Quotation money deposition for new service connection at Samanti PWSS P.H No- III , Dist-Howrah under ED PHED. Application No.-1007542321 dated- 17/02/2024 Ref. ID.- 106478203 |  |  | BILL/06164/2023-2024 | 797 | 23/02/2024 | 23/02/2024 | WBSEDCL | 3.59 | 0 | 0 | 0
6 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Work Order for Construction of Pump House, Boundary Wall,700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Rising Main , Laying Distribution Pipeline & Provinding FHTC (6865 nos) For Samanti PWSS at Panchla Block under Howrah Sadar sub Division of Howrah Division, P. H. E. DTE. | AE/SADAR | je_how_rws_jagat | ORD/000562/2022-2023 | 2500/HD | 30/11/2022 | 19/11/2025 | M/S S.S. ENTERPRISE | 789.11 | 433.49 | 54.93 | 40
7 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Additional Laying Distribution Pipeline & Adopting 2 nos Jack Pushing of 700 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 198-200 & 53-200 of LDS drawing) on Ranihati-Amta Road of Samanti PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/12562) | AE/SADAR | je_how_rws_jagat | ORD/000068/2024-2025 | 3106/HD | 08/07/2024 | 01/10/2025 | M/S S.S. ENTERPRISE | 459.55 | 228.52 | 49.73 | 65
8 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Sinking 2nos. 300 X 200 mm dia and 230 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 45m. long PVC housing pipe & 200 mm dia. 155m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Samanti PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000067/2025-2026 | 2574/HD | 02/06/2025 | 29/11/2025 | G.T.AGRO CENTRE | 36.04 | 0 | 0 | 0
9 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Panchla Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000639/2023-2024 | 1207/HD | 11/03/2024 | 26/03/2024 | M/S SUPROVAT GHOSH | 1.54 | 1.31 | 84.81 | 100
10 | HOWRAH | Panchla | Howrah Division | Samanti Piped Water Supply Scheme with FHTC Block: Panchla, District - Howrah. | SM/12562 | New | Special repairing work for restoration of damage pavement caused by laying of pipe line from Node section 54 to 200 for the 4.05 km (PMGSY/PWD) road at Samanti PWSS under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte | AE/SADAR | je_how_rws_jagat | ORD/000180/2024-2025 | 4200/HD | 27/09/2024 | 25/01/2025 | WALL FORT INDIA | 59.86 | 0 | 0 | 100
Total | [13 empty] | 1737.52 | 701.42 | 40.37