## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Preparation of DPR for Augmentation of Bamunhati PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/000244/2022-2023 | 321/AE/USD | 16/08/2022 | 30/09/2022 | APEX ENGINEERING | 4.04 | 0 | 0 | 100
2 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part F :- LDS & FHTC of Southern Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000752/2022-2023 | 651/HD | 17/02/2023 | 03/04/2023 | M/S MITRA CONSTRUCTION | 35.66 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part H :- LDS & FHTC of Part II of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000754/2022-2023 | 653/HD | 17/02/2023 | 03/04/2023 | SUPRIYA MAHANTI MISRA | 22.76 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No.- I, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000244/2022-2023 | 911/ED | 22/02/2023 | 08/04/2023 | SAIKAT ENTERPRISE | 11.51 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part L :- LDS & FHTC of Part VI of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000758/2022-2023 | 657/HD | 17/02/2023 | 03/04/2023 | BISWAJIT SAMANTA | 15.72 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 120.09 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Laying Distribution System & Providing House Hold Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part C :- LDS & FHTC of Srirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000136/2023-2024 | 2749/HD | 28/07/2023 | 19/03/2025 | CREATION CONSTRUCTION | 176.47 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Renovation of boundary wall at old Headwork Site of Bamunhati W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E.Dte. | AE/Ulu | JE/USD | ORD/000672/2023-2024 | 3235/AE/USD | 12/03/2024 | 11/04/2024 | A.A ENTERPRISE | 3.07 | 0 | 0 | 100
9 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part B :- LDS & FHTC of Barbangalpur Village) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000751/2022-2023 | 649/HD | 17/02/2023 | 03/12/2025 | S. R. ENTERPRISE | 76.95 | 0 | 0 | 60
10 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part I :- LDS & FHTC of Part III of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000755/2022-2023 | 654/HD | 17/02/2023 | 18/09/2025 | ASHOKE ENGINEERING WORKS | 11.31 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part E :- LDS & FHTC of Norther Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000750/2022-2023 | 650/HD | 17/02/2023 | 21/03/2025 | B.M ENTERPRISE | 63.69 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part Q:- FHTC of Part XI ) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000762/2022-2023 | 661/HD | 17/02/2023 | 07/05/2025 | SR TRADING CORPORATION | 3.98 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part G :- LDS & FHTC of Part I of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000753/2022-2023 | 652/HD | 17/02/2023 | 02/10/2025 | JOY GURU TRADING | 38.68 | 0 | 0 | 75
14 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000881/2022-2023 | 1195/HD | 23/03/2023 | 17/07/2025 | ACME CONSTRUCTION | 90.87 | 0 | 0 | 85
15 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Laying Distribution System & Providing House Hold Tap Connection (FHTC) & AugmeConstruction of 500cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of Bamunhati Piped Water Supply Scheme (Part A :- Bamunhati Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000011/2023-2024 | 1594/HD | 12/04/2023 | 27/11/2025 | M/S SRIKANTA PATRA | 219.51 | 0 | 0 | 30
16 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Laying Distribution System & Providing Household Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part D :-LDS & FHTC of Mahishrekha Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000106/2023-2024 | 2697/HD | 24/07/2023 | 10/03/2026 | CONSTRUCTION CORNER | 104.49 | 0 | 0 | 60
17 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Bamunhati PWSS (2nd Tube well) of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000778/2024-2025 | 1464/HD | 19/03/2025 | 03/05/2025 | NOBLE ENTERPRISE | 5.9 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Construction of switch room SLOPE ROOF (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Bamunhati PWSS of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000621/2024-2025 | 1207/HD | 04/03/2025 | 18/04/2025 | M/S SRIKANTA PATRA | 7.05 | 0 | 0 | 0
19 | HOWRAH |  | Electrical | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No. III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003615/2023-2024 | 3465/ED | 11/08/2023 | 09/11/2023 | B.T. PROJECT PVT. LTD. | 23.5 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part J :- LDS & FHTC of Part IV of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000756/2022-2023 | 655/HD | 17/02/2023 | 04/07/2025 | ABONTICA ENTERPRISE | 27.96 | 0 | 0 | 100
21 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part O:-LDS & FHTC of Part-IX of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000749/2022-2023 | 648/HD | 17/02/2023 | 20/06/2025 | JHARNA ENTERPRISE | 11.08 | 0 | 0 | 100
22 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part P:- LDS & FHTC of Part X of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000761/2022-2023 | 660/HD | 17/02/2023 | 04/10/2025 | KALIDAS ENTERPRISE | 3.99 | 0 | 0 | 100
23 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part K :- LDS & FHTC of Part V of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000757/2022-2023 | 656/HD | 17/02/2023 | 05/04/2025 | LOKENATH ENTERPRISES | 13.99 | 0 | 0 | 100
24 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part M :- LDS & FHTC of Part VII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000759/2022-2023 | 658/HD | 17/02/2023 | 23/03/2025 | ARINDAM ENTERPRISE | 22.22 | 0 | 0 | 100
25 | HOWRAH |  | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part N:- LDS & FHTC of Part VIII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000760/2022-2023 | 659/HD | 17/02/2023 | 21/06/2025 | S.B ENTERPRISE | 10.66 | 0 | 0 | 100
Total | [13 empty] | 1125.16 | 0 | 0