## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Ichhapur PWSS (Mouza-Ichhapur, Ranmahal & Tripurapur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000073/2022-2023 | 1016/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 3.04 | 0 | 0 | 0
2 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 12.32 | 0 | 0 | 0
3 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000694/2022-2023 | 312/HD | 20/01/2023 | 19/02/2023 | ALLIED TUBEWELLS PRIVATE LIMITED | 25.64 | 0 | 0 | 0
4 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 12.27 | 0 | 0 | 0
5 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Laying Distribution Pipeline (PART-2) & Providing FHTC (PART-2) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Jagatballavpur,JE/RWS/Panchla | ORD/000021/2023-2024 | 1674/HD | 19/04/2023 | 18/06/2023 | PIKASU BOSE | 149.08 | 0 | 0 | 60
6 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection For Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000870/2022-2023 | 1347/HD | 27/03/2023 | 21/01/2024 | RANI CONSTRUCTION | 91.61 | 0 | 0 | 10
7 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Continuation order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P.H.E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000314/2023-2024 | 4254/HD | 28/11/2023 | 28/12/2023 | AUXILIARY TUBEWELL DRILLERS | 25.64 | 0 | 0 | 100
8 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1317/HD | 14/03/2024 | 14/03/2024 | Resource Division | 17.52 | 0 | 0 | 0
9 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 4348/HD | 30/09/2024 | 30/09/2024 | Resource Division | 24.66 | 0 | 0 | 0
10 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Quotation money deposition for new service connection at Ichhapur pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007566560 Ref.ID: 106496241 SM/13629 |  |  | BILL/06259/2023-2024 | 859 | 11/03/2024 | 11/03/2024 | WBSEDCL | 17.26 | 0 | 0 | 0
11 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Quotation Money deposition for new service connection at Ichapur pwss, P.H No.-I , Dist-Howrah under ED PHED. Application No.- 1007513772 Ref. ID- 106460039 |  |  | BILL/06102/2023-2024 | 761 | 16/02/2024 | 16/02/2024 | WBSEDCL | 17.39 | 0 | 0 | 0
12 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ichapur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000127/2022-2023 | 3541/ED | 30/12/2022 | 14/12/2025 | KASHINATH PAL & CO. | 21.15 | 0 | 0 | 60
13 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Construction of 2 nos Pump House ( 5.40m x 3.60 m), 2nos Construction of Boundary Walls, Rising Main Pipeline Work, Laying Distribution Pipeline (Part-1) & Providing FHTC(Part-1) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division,PHE DTE (PART-I) | AE/SADAR | JE/RWS/Panchla | ORD/000796/2022-2023 | 977/HD | 10/03/2023 | 26/08/2025 | D D CONSTRUCTION | 110.53 | 0 | 0 | 10
14 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Restoration of road and Ancillary work for Ichapur PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000527/2024-2025 | 1068/HD | 27/02/2025 | 27/06/2025 | MAITY CONSTRUCTION | 20.84 | 0 | 0 | 0
Total | [13 empty] | 548.96 | 0 | 0