## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Hizlok Head Work Site and 2nd TW Site at Hizlok PWSS of Bagnan-I Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/13747) | AE/Ulu | je/blk/bagn1 | ORD/000133/2024-2025 | 4034/HD | 17/09/2024 | 16/12/2024 | AQUATECH ENGINEER | 28.95 | 3.84 | 13.27 | 45
2 | HOWRAH | Bagnan-I | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Preparation of DPR for Hijlok PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu | JE-USD | ORD/000366/2022-2023 | 461/AE/USD | 15/09/2022 | 30/10/2022 | DULAL MAJUMDER | 2.97 | 0 | 0 | 100
3 | HOWRAH | Bagnan-I | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Additional laying distribution pipeline with FHTC at Bagur & Paschim Bainan Mouza part of Paschim Bainan PWSS adjoining to Hizlak PWSS of Bagnan-I Block in Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000204/2024-2025 | 4514/HD | 04/10/2024 | 18/11/2024 | JOY CHANDI CONSTRUCTION | 48.54 | 34.23 | 70.51 | 100
4 | HOWRAH | Bagnan-I | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 1.54 | 0 | 0 | 0
5 | HOWRAH | Bagnan-I | Electrical | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Quotation for new service connection for Hijlak Piped Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. (SM/13747), Reference Id- 106636949, Application no- 1007864377 |  |  | BILL/00918/2024-2025 | 257 | 03/07/2024 | 03/07/2024 | WBSEDCL | 5.55 | 0 | 0 | 0
6 | HOWRAH | Bagnan-I | Electrical | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hijlak water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000257/2022-2023 | 924/ED | 22/02/2023 | 01/09/2025 | MENAKA ENTERPRISE | 20.27 | 0 | 0 | 40
7 | HOWRAH | Bagnan-I | Howrah Division | Hijlak Piped Water Supply Scheme in Bagnan-I block under Howrah district | SM/13747 | New | Work order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design & Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site HIjlak PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | je/blk/bagn1 | ORD/000105/2023-2024 | 2696/HD | 24/07/2023 | 24/07/2026 | PRADIP KUMAR JATI | 293.89 | 75.84 | 25.81 | 1
Total | [13 empty] | 401.71 | 113.91 | 28.36