## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Work Order for Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gopalpur PWSS 2nos & Patinan PWSS 2 Nos of Bagnan - I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu |  | ORD/000745/2022-2023 | 663/HD | 17/02/2023 | 03/04/2023 | AQUATECH ENGINEER | 52.06 | 23.58 | 45.29 | 100
2 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 36.34 | 0 | 0 | 0
3 | HOWRAH | Bagnan-I | Electrical | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Quotation Bill for New Service Connection at Uttar Gpalpur W/S. Sch. PH-I |  |  | BILL/04328/2023-2024 | 441 | 24/11/2023 | 24/11/2023 | WBSEDCL | 3.46 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Electrical | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. TW-I |  |  | BILL/04134/2023-2024 | 387 | 01/11/2023 | 01/11/2023 | WBSEDCL | 4.27 | 0 | 0 | 0
5 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & 300 cu.m. capacity 20mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design & Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site GOPALPUR PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/RWS/Bagnan I | ORD/000063/2023-2024 | 1917/HD | 08/05/2023 | 27/12/2024 | PRAVAT SARKAR | 335.59 | 0 | 0 | 16
6 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Preparation of DPR for Gopalpur PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu | JE-USD | ORD/000364/2022-2023 | 459/AE/USD | 15/09/2022 | 30/10/2022 | DULAL MAJUMDER | 3.14 | 0 | 0 | 100
7 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Site clearence of HW site of Gopalpur & Patinan PWSS under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000693/2023-2024 | 3244/AE/USD | 12/03/2024 | 11/04/2024 | S R TRADING CORPORATION | 0.96 | 0.96 | 99.55 | 100
8 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Bagnan-I & II Block of Uluberia Sub-Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000636/2023-2024 | 1206/HD | 11/03/2024 | 26/03/2024 | KULTIKARI MOTHER TERESA SOCIAL WELLFARE SOCIETY | 2.01 | 2.01 | 100 | 100
9 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 4.87 | 0 | 0 | 0
10 | HOWRAH | Bagnan-I | Electrical | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Quotation bill for service connection charges at Gopalpur w/s scheme, Zone-II, P.H. No.-II, Dist: Hooghly Application No.- 5004035005 Ref Id: 503576015 |  |  | BILL/06263/2023-2024 | 864 | 12/03/2024 | 12/03/2024 | WBSEDCL | 4.15 | 0 | 0 | 0
11 | HOWRAH | Bagnan-I | Electrical | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000125/2022-2023 | 3539/ED | 30/12/2022 | 01/11/2025 | KARTICK BAL | 20.35 | 13.72 | 67.42 | 60
12 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0.67 | 5.27 | 100
13 | HOWRAH | Bagnan-I | Howrah Division | Gopalpur Piped Water Supply Scheme | SM/13748 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ | je_blk_ballyjag_how | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 30/04/2026 | TECH VISION | 21.25 | 0 | 0 | 22
Total | [13 empty] | 501.1 | 40.93 | 8.17