## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Electrical | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | SM/13749 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gabberia Mallik Bagan water supply scheme, T.W. No.- I, II & III, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000152/2022-2023 | 3538/ED | 30/12/2022 | 30/03/2023 | INDIA ENTERPRISE | 30.58 | 0 | 0 | 0
2 | HOWRAH | Panchla | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | SM/13749 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Gabberia PWSS (Mouza-Gabberia(CT) & Mallik Bagan (CT) of Panchla Block under Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000079/2022-2023 | 1022/HD | 05/05/2022 | 20/05/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.04 | 3.04 | 100 | 0
3 | HOWRAH | Panchla | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | SM/13749 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 59.98 | 0 | 0 | 0
4 | HOWRAH | Panchla | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | SM/13749 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 21.47 | 0 | 0 | 0
5 | HOWRAH | Panchla | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | SM/13749 | New | Work Order for Additional laying distribution Pipeline work of Gabberia Mallickbagan PWSS at Panchla Block,of Howrah Sadar Sub Division under Howrah Division , PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000069/2023-2024 | 1930/HD | 10/05/2023 | 02/05/2025 | ADITYA HAZRA | 52.7 | 0 | 0 | 30
6 | HOWRAH | Panchla | Howrah Division | GABBERIA-MALLIK BAGAN PIPED WATER SUPPLY SCHEME. | SM/13749 | New | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000148/2023-2024 | 2866/HD | 08/08/2023 | 03/02/2026 | SAMIRON GHOSH | 1986.19 | 12.25 | 0.62 | 30
Total | [13 empty] | 2153.97 | 15.29 | 0.71