## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Preparation of DPR for Barram Nagar PWSS, Uluberia-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000362/2022-2023 | 457/AE/USD | 15/09/2022 | 30/10/2022 | APEX ENGINEERING | 3.29 | 0 | 0 | 100
2 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 21.56 | 0 | 0 | 0
3 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 4695/HD | 26/12/2023 | 26/12/2023 | Resource Division | 12.29 | 0 | 0 | 0
4 | HOWRAH | Uluberia-II | Electrical | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Barramnagar water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000122/2022-2023 | 3534/ED | 30/12/2022 | 14/03/2025 | M/S S R ENTERPRISE | 20.38 | 0 | 0 | 60
5 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 3.14 | 0 | 0 | 0
6 | HOWRAH | Uluberia-II | Electrical | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Quotation money deposition for new service connection at Barramnagar pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007576971 Ref.ID: 106502484 SM/13750 |  |  | BILL/06262/2023-2024 | 865 | 12/03/2024 | 12/03/2024 | WBSEDCL | 27.26 | 0 | 0 | 0
7 | HOWRAH | Uluberia-II | Electrical | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Quotation Bill for New Service Connection at Barramnagar W/S. Sch. PH-I |  |  | BILL/05983/2023-2024 | 728 | 05/02/2024 | 05/02/2024 | WBSEDCL | 8.74 | 0 | 0 | 0
8 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000881/2022-2023 | 1195/HD | 23/03/2023 | 17/07/2025 | ACME CONSTRUCTION | 90.87 | 0 | 0 | 85
9 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No- PC I/O.H.R/7/2012)with necessary soil investigation with foundation design as per soil test report for Barramnagar Piped Water Supply Scheme in Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000026/2023-2024 | 1691/HD | 20/04/2023 | 19/04/2026 | PRADIP KUMAR JATI | 316.16 | 0 | 0 | 38
10 | HOWRAH | Uluberia-II | Howrah Division | BARRAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/13750 | New | Construction of Culvert over the Drainage Chanal at Head Work site of Barramnagar PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Division PHED. | AE/Ulu |  | ORD/000730/2024-2025 | 1350/HD | 11/03/2025 | 25/04/2025 | PRADIP KUMAR JATI | 29.62 | 0 | 0 | 0
Total | [13 empty] | 533.31 | 0 | 0