## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 47.46 | 0 | 0 | 0
2 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. Z-i |  |  | BILL/04500/2023-2024 | 546 | 19/12/2023 | 19/12/2023 | WBSEDCL | 9.63 | 0 | 0 | 0
3 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P.H.E. DTE | AE/SADAR | JE Sadar | ORD/000774/2022-2023 | 795/HD | 27/02/2023 | 28/05/2023 | UNIVERSAL CORPORATION | 143.99 | 103.61 | 71.96 | 50
4 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000251/2022-2023 | 918/ED | 22/02/2023 | 23/05/2023 | D. K. ELECTRIC | 32.22 | 10.46 | 32.47 | 30
5 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) in DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR | je6/maad,JE Sadar | ORD/000814/2022-2023 | 981/HD | 13/03/2023 | 09/09/2023 | MA MANASA CONSTRUCTION | 148.59 | 70.33 | 47.33 | 48
6 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 19.07 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Shifting of 1 (No.) 25kva DISTRIBUTION SUB-STATATION at Dakshin Jhapordah (Zone-I) PWSS, P.H No.-I under ED, PHED. Ref. ID.-860318414 SM/13751 |  |  | BILL/02300/2024-2025 | BP-24-25-595 | 21/11/2024 | 21/11/2024 | WBSEDCL | 1.71 | 0 | 0 | 0
8 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line from Panchanantala to Taruner Ahaban Club Road & Radharani Laha Memorial School to bisalaxmitala Road of Domjur (Zone-4) Dakshin Jhapardaha (Zone-I) PWSS under Howrah Sadar Sub-Divnision PHE Dte. | AE/SADAR | JE Sadar | ORD/000098/2025-2026 | 2955/HD | 26/06/2025 | 24/09/2025 | USHA CONCERN | 39.78 | 0 | 0 | 100
Total | [13 empty] | 442.45 | 184.4 | 41.68