## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 47.46 | 0 | 0 | 0
2 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. Z-i |  |  | BILL/04500/2023-2024 | 546 | 19/12/2023 | 19/12/2023 | WBSEDCL | 9.63 | 0 | 0 | 0
3 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P.H.E. DTE | AE/SADAR | JE Sadar | ORD/000774/2022-2023 | 795/HD | 27/02/2023 | 28/05/2023 | UNIVERSAL CORPORATION | 143.99 | 0 | 0 | 50
4 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000251/2022-2023 | 918/ED | 22/02/2023 | 23/05/2023 | D. K. ELECTRIC | 32.22 | 0 | 0 | 30
5 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000664/2022-2023 | 175/HD | 13/01/2023 | 26/10/2025 | B K ENTERPRISE | 77.78 | 0 | 0 | 50
6 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) in DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR | je6/maad,JE Sadar | ORD/000814/2022-2023 | 981/HD | 13/03/2023 | 09/09/2023 | MA MANASA CONSTRUCTION | 148.59 | 0 | 0 | 48
7 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 19.07 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Shifting of 1 (No.) 25kva DISTRIBUTION SUB-STATATION at Dakshin Jhapordah (Zone-I) PWSS, P.H No.-I under ED, PHED. Ref. ID.-860318414 SM/13751 |  |  | BILL/02300/2024-2025 | BP-24-25-595 | 21/11/2024 | 21/11/2024 | WBSEDCL | 1.71 | 0 | 0 | 0
9 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13751 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 14/12/2025 | TECH VISION | 8.36 | 0 | 0 | 79
Total | [13 empty] | 488.8 | 0 | 0