## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR | je6/maad | ORD/000765/2022-2023 | 722/HD | 23/02/2023 | 24/05/2023 | FAITH ENTERPRISE | 135.21 | 64.34 | 47.59 | 50
2 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000234/2022-2023 | 87/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.7 | 3.7 | 100 | 100
3 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000233/2022-2023 | 86/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.04 | 3.04 | 100 | 100
4 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-II) PWSS (Mouza-Mollar Chak, Chak Narna, Parbatipur, Uttar Jhapardaha (CT) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000235/2022-2023 | 88/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.86 | 3.81 | 98.72 | 100
5 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 87.43 | 0 | 0 | 0
6 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Deposition of quotation money for domjur(zone-iv) dakshin jhapardaha( zone-ii) water supply scheme , P.H No.-I,Dist-Howrah umder ED, PHED. |  |  | BILL/00752/2023-2024 |  | 12/05/2023 | 12/05/2023 | WBSEDCL | 0.73 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | New service connection |  |  | BILL/02058/2023-2024 | 108 | 19/07/2023 | 19/07/2023 | WBSEDCL | 4.03 | 0 | 0 | 0
8 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 557, 562 to 667) [PART-4]. | AE/SADAR | je6/maad,JE Sadar | ORD/000670/2022-2023 | 162/HD | 13/01/2023 | 14/03/2023 | CHAKRABORTY ENTERPRISE | 50.34 | 48.39 | 96.12 | 15
9 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000664/2022-2023 | 175/HD | 13/01/2023 | 15/03/2025 | B K ENTERPRISE | 77.78 | 25.23 | 32.43 | 50
10 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 530 to 561) [PART-5]. | AE/SADAR | je6/maad,JE Sadar | ORD/000682/2022-2023 | 270/HD | 19/01/2023 | 20/03/2023 | PBA INFRASTRUCTURE | 15.34 | 14.62 | 95.3 | 35
11 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 350 to 530) [PART-3]. | AE/SADAR | je6/maad,JE Sadar | ORD/000669/2022-2023 | 161/HD | 13/01/2023 | 14/03/2023 | BUILT INDIA | 77.96 | 68.65 | 88.06 | 50
12 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Dakshin Jhapardaha (Zone-4) PWSS (Zone-II) at 2nd & 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000627/2023-2024 | 1213/HD | 11/03/2024 | 25/04/2024 | CHANDIMATA CONSTRUCTION | 15.45 | 0 | 0 | 100
13 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 22.21 | 0 | 0 | 0
14 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. |  |  | BILL/04634/2023-2024 | 629 | 08/01/2024 | 08/01/2024 | WBSEDCL | 3.61 | 0 | 0 | 0
15 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Quotation money deposition for new service connection at Domjur(Zone-IV) w/s scheme, Dakshin Jhapordaha(Zone-II), Pwss, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008185043 Reference ID- 106810747 SM Code- 13752 |  |  | BILL/02127/2024-2025 | 571 | 13/11/2024 | 13/11/2024 | WBSEDCL | 5.47 | 0 | 0 | 0
16 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR | je6/maad,JE Sadar | ORD/000775/2022-2023 | 812/HD | 28/02/2023 | 23/02/2025 | M/S CHANDIMATA CONSTRUCTION | 151.7 | 110.54 | 72.87 | 40
17 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 8.36 | 1.27 | 15.21 | 79
18 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-II) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000249/2022-2023 | 916/ED | 22/02/2023 | 22/05/2025 | M.S. ENTERPRISE | 32.73 | 21.13 | 64.54 | 40
Total | [13 empty] | 698.93 | 364.71 | 52.18