## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR | je6/maad | ORD/000765/2022-2023 | 722/HD | 23/02/2023 | 24/05/2023 | FAITH ENTERPRISE | 135.21 | 64.34 | 47.59 | 50
2 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000234/2022-2023 | 87/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.7 | 3.7 | 100 | 100
3 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000233/2022-2023 | 86/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.04 | 3.04 | 100 | 100
4 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-II) PWSS (Mouza-Mollar Chak, Chak Narna, Parbatipur, Uttar Jhapardaha (CT) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000235/2022-2023 | 88/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.86 | 3.81 | 98.72 | 100
5 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 87.43 | 0 | 0 | 0
6 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Deposition of quotation money for domjur(zone-iv) dakshin jhapardaha( zone-ii) water supply scheme , P.H No.-I,Dist-Howrah umder ED, PHED. |  |  | BILL/00752/2023-2024 |  | 12/05/2023 | 12/05/2023 | WBSEDCL | 0.73 | 0 | 0 | 0
7 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | New service connection |  |  | BILL/02058/2023-2024 | 108 | 19/07/2023 | 19/07/2023 | WBSEDCL | 4.03 | 0 | 0 | 0
8 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 557, 562 to 667) [PART-4]. | AE/SADAR | je6/maad,JE Sadar | ORD/000670/2022-2023 | 162/HD | 13/01/2023 | 25/08/2025 | CHAKRABORTY ENTERPRISE | 50.34 | 48.39 | 96.12 | 15
9 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 350 to 530) [PART-3]. | AE/SADAR | je6/maad,JE Sadar | ORD/000669/2022-2023 | 161/HD | 13/01/2023 | 14/03/2023 | BUILT INDIA | 77.96 | 68.65 | 88.06 | 50
10 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Dakshin Jhapardaha (Zone-4) PWSS (Zone-II) at 2nd & 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000627/2023-2024 | 1213/HD | 11/03/2024 | 25/04/2024 | CHANDIMATA CONSTRUCTION | 15.45 | 0 | 0 | 100
11 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 22.21 | 0 | 0 | 0
12 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. |  |  | BILL/04634/2023-2024 | 629 | 08/01/2024 | 08/01/2024 | WBSEDCL | 3.61 | 0 | 0 | 0
13 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Quotation money deposition for new service connection at Domjur(Zone-IV) w/s scheme, Dakshin Jhapordaha(Zone-II), Pwss, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008185043 Reference ID- 106810747 SM Code- 13752 |  |  | BILL/02127/2024-2025 | 571 | 13/11/2024 | 13/11/2024 | WBSEDCL | 5.47 | 0 | 0 | 0
14 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-II) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000249/2022-2023 | 916/ED | 22/02/2023 | 22/05/2025 | M.S. ENTERPRISE | 32.73 | 21.13 | 64.54 | 40
15 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR | je6/maad,JE Sadar | ORD/000775/2022-2023 | 812/HD | 28/02/2023 | 23/02/2025 | M/S CHANDIMATA CONSTRUCTION | 151.7 | 110.54 | 72.87 | 40
16 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000111/2024-2025 | 3730/HD | 29/08/2024 | 28/09/2024 | HORIZEN | 4.93 | 0 | 0 | 100
17 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Rising Main Pipeline Work From 2nd Pump House to 1st Pump House Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) PWSS at Domjur Block Of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000147/2024-2025 | 4129/HD | 23/09/2024 | 07/11/2024 | M/S. CHANDIMATA CONSTRUCTION | 36.07 | 0 | 0 | 100
18 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Domjur - Andul Road from 0.00 Km to 4.129 Km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the district of Howrah (Dakshin Jhapardaha PWSS Zone-II, Dakshin Jhapardaha PWSS Zone-I, Bhandardaha PWSS, Bipranoapara PWSS). |  |  | BILL/01249/2024-2025 |  | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 101.31 | 0 | 0 | 0
19 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000664/2022-2023 | 175/HD | 13/01/2023 | 24/04/2026 | B K ENTERPRISE | 77.78 | 25.23 | 32.43 | 85
20 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 530 to 561) [PART-5]. | AE/SADAR | je6/maad,JE Sadar | ORD/000682/2022-2023 | 270/HD | 19/01/2023 | 01/08/2024 | PBA INFRASTRUCTURE | 15.34 | 14.62 | 95.3 | 100
21 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 13/04/2026 | TECH VISION | 8.36 | 1.27 | 15.21 | 95
22 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-IV) Dakshin Jhapardaha (Z-II) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/13752 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) PWSS [SM/13751], Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) PWSS [SM/13752], Keshabpur PWSS [SM/16947] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000972/2024-2025 | 222/HSSD | 25/02/2025 | 12/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
Total | [13 empty] | 842.11 | 364.71 | 43.31