## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Paschim Panchla PWSS (Mouza-Paschim Panchla(CT) & Dakshin Panchla) of Panchla Block under Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000078/2022-2023 | 1021/HD | 05/05/2022 | 20/05/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.13 | 100 | 100
2 | HOWRAH | Panchla,Uluberia-II | Electrical | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Quotation Bill for New Service Connection at Paschim Panchla W/S. Sch. PH-II |  |  | BILL/04336/2023-2024 | 446 | 28/11/2023 | 28/11/2023 | WBSEDCL | 22.73 | 0 | 0 | 0
3 | HOWRAH | Panchla,Uluberia-II | Electrical | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Quotation Bill for New Service Connection at Paschim Panchla W/S. Sch. PH-I |  |  | BILL/04335/2023-2024 | 445 | 28/11/2023 | 28/11/2023 | WBSEDCL | 23.36 | 0 | 0 | 0
4 | HOWRAH | Panchla,Uluberia-II | Electrical | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Panchla water supply scheme, T.W. No. I, II & III, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000037/2023-2024 | 1714/ED | 18/04/2023 | 17/07/2023 | S.P. CONSTRUCTION | 30.56 | 19.82 | 64.84 | 40
5 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 12.18 | 0 | 0 | 0
6 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 1094/HD | 05/03/2024 | 05/03/2024 | Resource Division | 45.31 | 0 | 0 | 0
7 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 1094/HD | 05/03/2024 | 05/03/2024 | Resource Division | 29.4 | 0 | 0 | 0
8 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 843/HD | 22/02/2024 | 22/02/2024 | Resource Division | 22.18 | 0 | 0 | 0
9 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000148/2023-2024 | 2866/HD | 08/08/2023 | 03/02/2026 | SAMIRON GHOSH | 1986.19 | 241.58 | 12.16 | 30
10 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Additional Laying Distribution Pipeline & approach road with land development at OHR site & allied works of Paschim Panchla PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (SM/13768) | AE/SADAR | je_how_rws_jagat | ORD/000026/2024-2025 | 2828/HD | 20/06/2024 | 14/08/2025 | SAMIRON GHOSH | 130.84 | 0 | 0 | 20
11 | HOWRAH | Panchla,Uluberia-II | Howrah Division | Paschim Panchla Piped Water Supply Scheme. | SM/13768 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 12.48 | 0 | 0 | 62
Total | [13 empty] | 2318.37 | 264.53 | 11.41