## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Nimabalia PWSS (Mouza-Moulagachhi, Finga Gachhi, Marghurali & Nimabalia) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000074/2022-2023 | 1017/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 3.31 | 3.31 | 100 | 100
2 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nimabalia PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000695/2022-2023 | 313/HD | 20/01/2023 | 19/02/2023 | R CONSTRUCTION | 25.64 | 25.52 | 99.51 | 100
3 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Construction of Culvert & Approach Road at Nimabalia OHR Site under Nimabalia PWSS in J.B Pur Block under Howrah Division PHE Dte. Howrah. | AE/SADAR |  | ORD/000071/2023-2024 | 1932/HD | 10/05/2023 | 09/07/2023 | TRADE GREEN | 7.11 | 7.11 | 99.97 | 100
4 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 18.43 | 0 | 0 | 0
5 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-I |  |  | BILL/01298/2022-2023 | 189 | 16/03/2023 | 16/03/2023 | WBSEDCL | 7.62 | 0 | 0 | 0
6 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-2 |  |  | BILL/00020/2023-2024 | 04 | 13/04/2023 | 13/04/2023 | WBSEDCL | 3.17 | 0 | 0 | 0
7 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Additional quotation money deposit for Nimabalia w/s scheme. P.H-I, dist-howrah under ED/PHED. |  |  | BILL/00747/2023-2024 | 35 | 12/05/2023 | 12/05/2023 | WBSEDCL | 3.97 | 0 | 0 | 0
8 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nimabalia water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000119/2022-2023 | 3544/ED | 30/12/2022 | 30/03/2023 | GHOSE ENGINEERING SYNDICATE | 22.59 | 21.67 | 95.9 | 75
9 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Construction of 2 Nos. Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Sites Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Laying Distribution Pipeline, providing Functional Household Tap Connection(FHTC) & Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR for NIMABALIA PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=850] | AE/SADAR | je_how_rws_jagat | ORD/000200/2023-2024 | 3257/HD | 11/09/2023 | 09/03/2024 | GHOSH ENTERPRISE. | 175.9 | 174.53 | 99.23 | 60
10 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Land Development at OHR site & allied works at Nimabalia PWSS of J.B.Pur Block under Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000033/2024-2025 | 640/HSSD | 25/06/2024 | 25/07/2024 | TRADE GREEN | 4.8 | 4.8 | 99.96 | 100
11 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 15.21 | 0 | 0 | 0
12 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Quotation money deposition for shifting of L.T O.H along with service cable at Nimabalia P.H No-I , Dist-Howrah under ED PHED. App. No.-100000101729 Ref I.D : 860293289 SM/13770 |  |  | BILL/06282/2023-2024 | 879 | 13/03/2024 | 13/03/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
13 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Construction Of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Nimabalia PWSS at Jagatballavpur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000028/2023-2024 | 1697/HD | 21/04/2023 | 07/10/2025 | RAYCON CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 121.92 | 30.11 | 24.69 | 10
14 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Making of T.W. Foundation at Nimabalia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003571/2023-2024 | 3455/HMSD | 20/12/2023 | 27/12/2023 | GHOSE ENGINEERING SYNDICATE | 0.96 | 0.96 | 100 | 0
15 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Laying distribution system (LDS) of existing drawing for 225 mm dia from (Node point J127-J488), for 200 mm dia (Node point J136-J144), for 180 mm dia (Node point J144-J148), for 160 mm dia (Node point J148-J508 & J10-J17), for 140 mm dia (Node point J152-J510 & J10-J01), for 125 mm dia (Node point J160-J167 & J17-J21), for 110 mm dia (Node point J17-J552), for 90 mm dia (Node point J330-J187) with 712 nos. Functional household tap connection (FHTC) and aproach road with land development at 2nd tube well site & allied works of Nimabalia PWSS at J.B. Pur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division PHE Dte. (SM/13770) | AE/SADAR | je_how_rws_jagat | ORD/000025/2024-2025 | 2820/HD | 20/06/2024 | 16/01/2025 | GHOSH ENTERPRISE | 127.58 | 76.14 | 59.68 | 40
16 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 13/04/2026 | HORIZEN | 10.11 | 0 | 0 | 56
17 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Supplying,fitting,fixing and erecting of Display Board at Shekrahati PWSS [SM/09586], Nimabalia PWSS [SM/13770], Shyampur PWSS [SM/11790] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000983/2024-2025 | 231-A/HSSD | 28/02/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
Total | [13 empty] | 549.81 | 344.14 | 62.59