## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Preparation of DPR for Khadinan PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu | JE/USD | ORD/000363/2022-2023 | 458/AE/USD | 15/09/2022 | 30/10/2022 | DULAL MAJUMDER | 3.16 | 0 | 0 | 100
2 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Work Order for Renovation of 2nd Pump House along with Land Development work for Khadinan piped water supply scheme of Bagnan-I Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000078/2023-2024 | 1776/HD | 27/04/2023 | 11/06/2023 | LOKENATH ENTERPRISES | 4.2 | 0 | 0 | 100
3 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 13.49 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Shifting and stacking of serviceable and unserviceable pipes and specials within the campus ofUluberia Sub-Division office campus including construction of wall racks and shelves almirah for keeping the office records in safe position in connection with "Khadinan PWSS" of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000649/2023-2024 | 3223/AE/USD | 12/03/2024 | 11/04/2024 | S R TRADING CORPORATION | 2.16 | 0 | 0 | 100
5 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 7.95 | 0 | 0 | 0
6 | HOWRAH | Bagnan-I | Electrical | Khadinan Piped Water Supply Scheme | SM/13847 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khadinan water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000118/2022-2023 | 3543/ED | 30/12/2022 | 01/03/2025 | ANJAN ENTERPRISE | 22.15 | 0 | 0 | 50
7 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No- PC-I/O.H.R/7/2012) including Pipe connection & soil investigation with foundation design as per soil test report for Khadinan PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000110/2023-2024 | 2074/HD | 24/05/2023 | 01/04/2026 | D D CONSTRUCTION | 384.72 | 0 | 0 | 65
8 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-I Block) | AE HQ |  | ORD/000229/2025-2026 | 4127/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
9 | HOWRAH | Bagnan-I | Howrah Division | Khadinan Piped Water Supply Scheme | SM/13847 | New | Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep Replace HW site tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khadian PWSS of Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000136/2024-2025 | 4062/HD | 18/09/2024 | 02/12/2024 | LOKENATH ENTERPRISES | 14.58 | 0 | 0 | 100
Total | [13 empty] | 457.2 | 0 | 0