## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supply, delivery of clamp on type portable Flowmeter set for different OHR site of Bargachia water supply scheme, Howrah under Electrical Division, PHE Dte. |  |  | ORD/000083/2023-2024 | 2157/ED | 16/06/2023 | 15/08/2023 | SHANTA COLIBRI (INDIA) PVT. LTD | 17.68 | 17.68 | 100 | 100
2 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Sinking of 2 (One) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS ZONE -X (TW I,II) of Jagatballavpur Block under Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000691/2022-2023 | 309/HD | 20/01/2023 | 19/02/2023 | NADIA TUBEWELLS | 34.37 | 31.55 | 91.81 | 100
3 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 282.87 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | new service connection |  |  | BILL/03696/2023-2024 | 243 | 01/09/2023 | 01/09/2023 | WBSEDCL | 5.82 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachia W/S. Sch. Z-V |  |  | BILL/04567/2023-2024 | 570 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.23 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | New service connection |  |  | BILL/02059/2023-2024 | 106 | 19/07/2023 | 19/07/2023 | WBSEDCL | 7.45 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | new service connection |  |  | BILL/03698/2023-2024 | 244 | 01/09/2023 | 01/09/2023 | WBSEDCL | 5.93 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Payment for WBSEDCL Augmentation of Bargachia Water Supply Scheme (Zone-IV) Pump house no -II |  |  | BILL/00242/2023-2024 | BP-2023-24-74 | 13/06/2023 | 13/06/2023 | WBSEDCL | 3.37 | 0 | 0 | 0
9 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachi W/S. Sch. Z-X, PH-I |  |  | BILL/04324/2023-2024 | 435 | 23/11/2023 | 23/11/2023 | WBSEDCL | 1.81 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachia W/S. Sch. Z-I |  |  | BILL/04568/2023-2024 | 571 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.55 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation Bill for New Service Connection at Bargachia PH-I, Z-VI W/S. Sch. |  |  | BILL/02327/2023-2024 | 146 | 26/07/2023 | 26/07/2023 | WBSEDCL | 4.96 | 0 | 0 | 0
12 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Deposition of quotation money for Aug.of Baragachia w/s scheme , zone-vi, P.H No-II Dist-Howrah under ED/PHED. |  |  | BILL/00740/2023-2024 | 24 | 11/05/2023 | 11/05/2023 | WBSEDCL | 11.06 | 0 | 0 | 0
13 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | New service connection |  |  | BILL/02060/2023-2024 | 107 | 19/07/2023 | 19/07/2023 | WBSEDCL | 3.43 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Payment for WBSEDCL Augmentation of Bargachia Water Supply Scheme (Zone-IV) Pump house no -I |  |  | BILL/00241/2023-2024 | BP-2023-24-74 | 13/06/2023 | 13/06/2023 | WBSEDCL | 3.91 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone VI (TW-1 &TW-II), Zone-VII (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je1_iu,je_how_rws_jagat | ORD/000687/2022-2023 | 307/HD | 20/01/2023 | 20/05/2023 | B K ENTERPRISE | 69.42 | 15.67 | 22.57 | 50
16 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone 1 (TW-1 &TW-II), Zone-II TW I&II at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000688/2022-2023 | 304/HD | 20/01/2023 | 21/03/2023 | CARBON SERVICES INDIA | 68.08 | 46.31 | 68.03 | 50
17 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Construction of Pump House, Boundary Wall, 400 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (2554 nos) For Augmentation of Bargachia PWSS (Zone-VII) in Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000486/2023-2024 | 454/HD | 01/02/2024 | 30/07/2024 | M/S ASHA CONSTRUCTION | 442.08 | 48.36 | 10.94 | 12
18 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Construction of R.C.C. Culvert at OHR site, Approach Road and Land Development at OHR Site, Retaining Wall at OHR site of Bargachia PWSS(Zone-VII) in J.B. Pur Block of Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000163/2024-2025 | 4195/HD | 26/09/2024 | 24/01/2025 | COSMO ENTERPRISE | 65.1 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Road restoration work, approach road and Land development at Over Head Reservoir Site, Construction of 1no Hume pipe culvert, RCC Retaining Wall & Jack Pushing of 700 mm dia M.S pipe as Casing Pipe to Cross Water carrier pipe (Between Node Point 81-82 of LDS drawing) at Bargachia zone-V & VI PWSS under Howrah Sadar Sub-Division of Howrah Division P.H.E.Dte. (SM/14095) | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000114/2024-2025 | 3871/HD | 04/09/2024 | 01/06/2025 | S.P. CONSTRUCTION | 227.58 | 0 | 0 | 30
20 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone VIII (TW-1 &TW-II), Zone-IX (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Panchla,JE Sadar | ORD/000690/2022-2023 | 308/HD | 20/01/2023 | 21/03/2023 | WATER TECH | 68.83 | 63.37 | 92.07 | 50
21 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 176.2 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1956/HD | 16/04/2024 | 16/04/2024 | Resource Division | 17.78 | 0 | 0 | 0
23 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 843/HD | 22/02/2024 | 22/02/2024 | Resource Division | 31.83 | 0 | 0 | 0
24 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation for New Service Connection at Bargachia W/S. Sch. Z=IX |  |  | BILL/04610/2023-2024 | 609 | 04/01/2024 | 04/01/2024 | WBSEDCL | 13.16 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS |  |  | BILL/00063/2024-2025 | BP-2024-25-19 | 26/04/2024 | 26/04/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.3 | 0 | 0 | 0
26 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Restoration Work of Bituminous Road and Shoulder with allied work Bargachia Boharia Road from 2.30 kmp to 6.30 kmp (Due to cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-2025. |  |  | BILL/00827/2024-2025 | BP-2024-25-495 | 27/11/2024 | 27/11/2024 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 34.15 | 0 | 0 | 0
27 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS, |  |  | BILL/00065/2024-2025 | BP-2024-25-20 | 23/04/2024 | 23/04/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.12 | 0 | 0 | 0
28 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Bill Document for Payment of Wayleave Plan & Survey Charges |  |  | BILL/00126/2024-2025 | BP-2024-25-68 | 16/05/2024 | 16/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.03 | 0 | 0 | 0
29 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Bill Document for Payment of Wayleave facility charges |  |  | BILL/00234/2024-2025 | BP-2024-25-121 | 11/06/2024 | 11/06/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 8.37 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Bill Document for Payment of Wayleave facility charges |  |  | BILL/00161/2024-2025 | BP-2024-25-100 | 28/05/2024 | 28/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 17.55 | 0 | 0 | 0
31 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quatation for shifting of H.T.O.H. Line DP to the PHE No- I, Zone- VI, Hantal sashan , Howrah under Bargachia CCC. Application No- 100000113194 Reference ID- 860304044 SM Code- 14095 |  |  | BILL/01269/2024-2025 | 331 | 30/07/2024 | 30/07/2024 | WBSEDCL | 5.83 | 0 | 0 | 0
32 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 8, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007566516 Reference ID- 106496242 SM Code- 14095 |  |  | BILL/06321/2023-2024 | 881 | 13/03/2024 | 13/03/2024 | WBSEDCL | 15.65 | 0 | 0 | 0
33 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- II, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008229574 Reference ID- 106837719 SM Code- 14095 |  |  | BILL/02606/2024-2025 | 627 | 18/12/2024 | 18/12/2024 | WBSEDCL | 16.23 | 0 | 0 | 0
34 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 9, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007604360 Reference ID- 106521117 SM Code- 14095 |  |  | BILL/00434/2024-2025 | 114 | 13/05/2024 | 13/05/2024 | WBSEDCL | 10.29 | 0 | 0 | 0
35 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Bill Document for payment of wayleave facility charges for Application ID : SER-KGP-2024-WL-34, Bargachia Zone-v |  |  | BILL/00110/2024-2025 | BP-2024-25-50 | 07/05/2024 | 07/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 7.37 | 0 | 0 | 0
36 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Bill Document for Payment of Wayleave facility charges |  |  | BILL/00160/2024-2025 | BP-2024-25-99 | 28/05/2024 | 28/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 6.22 | 0 | 0 | 0
37 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Payment for Way Leave and Survey Charges Bargachia PWSS |  |  | BILL/01656/2023-2024 | BP-2023-24-735 | 27/03/2024 | 27/03/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.13 | 0 | 0 | 0
38 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 4b, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007682963 Reference ID- 106564006 SM Code- 14095 |  |  | BILL/00454/2024-2025 | 130 | 17/05/2024 | 17/05/2024 | WBSEDCL | 17.99 | 0 | 0 | 0
39 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Post 5 years maintenance works for the road Begpara - Godaripara T06 at Jagatballavpur Block, Howrah under W.B.S.R.D.A. Howrah Division-I, Package No. WB/09/105. |  |  | BILL/00853/2024-2025 | BP-2024-25-504 | 09/12/2024 | 09/12/2024 | WBSRDA | 9.5 | 0 | 0 | 0
40 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation Money deposition for new service connection at Bargachia water supply scheme, Zone-8 ,P.H No.-I , Dist- Howrah under ED , PHED. |  |  | BILL/06035/2023-2024 | 736 | 07/02/2024 | 07/02/2024 | WBSEDCL | 10.61 | 0 | 0 | 0
41 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- III, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007550896 Reference ID- 106484781 SM Code- 14095 |  |  | BILL/06320/2023-2024 | 880 | 13/03/2024 | 13/03/2024 | WBSEDCL | 25.65 | 0 | 0 | 0
42 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS, |  |  | BILL/00067/2024-2025 | BP-2024-25-21 | 23/04/2024 | 23/04/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.11 | 0 | 0 | 0
43 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 500 cum Capacity OHR (2 nos), Rising Main, Laying Distribution Pipeline & Providing FHTC For AUGMENTATION OF Bargachia (ZONE-V and ZONE-VI) PWSS in Jagatballavpur Block under Howrah Sadar Sub-Division of HOWRAH DIVISION, P. H. E. DTE.. | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000634/2022-2023 | 05/HD | 02/01/2023 | 17/12/2025 | S.P. CONSTRUCTION | 1271.27 | 749.32 | 58.94 | 80
44 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 400 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (2554 nos) For AUGMENTATION OF Bargachia PWSS (ZONE-IX) in Jagatballavpur Block under Howrah Sadar Sub-Division of HOWRAH DIVISION, P.H.E. DTE. | AE/SADAR | JE/RWS/Panchla | ORD/000723/2022-2023 | 379/HD | 01/02/2023 | 20/07/2025 | G.B. CONSTRUCTION AND CO | 462.97 | 133.51 | 28.84 | 15
45 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 450 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (3187 nos) For Augmentation of Bargachia PWSS (Zone-VIII) in Jagatballavpur Block under Howrah Sadar sub Division of Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Panchla,JE Sadar | ORD/000708/2022-2023 | 336/HD | 24/01/2023 | 08/04/2026 | MONDAL PRECISION PVT. LTD. | 566.01 | 208.71 | 36.87 | 35
46 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 400 cum Capacity OHR , Rising Main , Laying Distribution Pipeline & Providing FHTC (1615 nos) For Augmentation of Bargachia PWSS (Zone-X) In Jagatballavpur Block under Howrah Sadar sub Division of Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Panchla,JE/RWS/Sankrail | ORD/000748/2022-2023 | 682/HD | 20/02/2023 | 22/04/2026 | B.B.C ENTERPRISE | 339 | 173.54 | 51.19 | 20
47 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 300, 400 & 500 cum capacity OHR, Rising Main Laying Distribution System & Providing FHTC for Augmentation of Bargachia (Zone-I, II, III, IV-A, IV-B) Piped Water Supply Scheme at Jagatballavpur Block under Howrah Division, PHE Dte in connection with JJM. | AE/SADAR | je6/maad,JE Sadar | ORD/000009/2023-2024 | 1559/HD | 06/04/2023 | 28/06/2025 | GREEN ROYAL INFRA CON PRIVATE LIMITED | 2577.67 | 1338.14 | 51.91 | 25
48 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of BARGACHIA Water Supply Scheme, Zone-I, II, III, IV(A), IV(B), V, VI, VII, VIII, IX, X. T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000768/2023-2024 | 2185/ED | 22/06/2023 | 22/06/2025 | J.D.J ENTERPRISE | 250.01 | 153.6 | 61.44 | 35
49 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Hiring of 1 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer Howrah Sadar Sub-Division, PHE Dte. Government of West Bengal. (for the period of 1 year)(for 365 days) | AE/SADAR | JE Sadar | ORD/000104/2024-2025 | 809/HSSD | 06/08/2024 | 06/08/2025 | MD KADIR | 4.73 | 3.57 | 75.5 | 8
50 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Construction of 1 no. Slab culvert,Construction of RCC Retaining Wall, construction of approch road and land Devlopment at Over Head Reservoir Site at Bargachia (Zone -VIII) PWSS Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000657/2023-2024 | 1246/HD | 12/03/2024 | 05/07/2025 | REALIENCE CONSTRUCTION | 36.2 | 0 | 0 | 11
51 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Additional work related to Augmentation of Bargachia PWSS (For Zone-X) under JJM for land development for Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000660/2023-2024 | 193/HSSD | 23/02/2024 | 19/03/2025 | S.B ENTERPRISE | 4.38 | 0 | 0 | 0
52 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone IVB (TW-1 &TW-II), Zone-V (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je1_iu,je6/maad,je_blk_ballyjag_how,JE Sadar | ORD/000689/2022-2023 | 306/HD | 20/01/2023 | 16/04/2025 | CARBON SERVICES INDIA | 68.08 | 48.38 | 71.05 | 100
53 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Road Restoration, Supply and Fabrication of 700 mm Dia, 7.10 mm thick MS Casing Pipe and Pushing of Casing Pipe by Hydraulic Jack Pushing Method, Construction of RCC Retaining Wall, Land Development, Construction of 1 No. Culvert and ancillary works at Bargachia PWSS (Zone-VII, VIII & IX) of J.B. Pur Block under Howrah Sadar Sub-Division, Howrah Division, P.H.E. Dte.(SM/14095) | AE/SADAR |  | ORD/000103/2025-2026 | 3057/HD | 08/07/2025 | 21/09/2025 | REALIENCE CONSTRUCTION | 413.83 | 0 | 0 | 0
54 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000111/2024-2025 | 3730/HD | 29/08/2024 | 28/09/2024 | HORIZEN | 4.93 | 0 | 0 | 100
55 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- V, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008227628 Reference ID- 106835520 SM Code- 14095 |  |  | BILL/02812/2024-2025 | 655 | 09/01/2025 | 09/01/2025 | WBSEDCL | 9.41 | 0 | 0 | 0
56 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Sifting Quotation as per as approval from DM HDD-II IRO E Office No.-400759 Application No- 100000138749 Reference ID- 860336080 SM Code- 14095 |  |  | BILL/01000/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 1.88 | 0 | 0 | 0
57 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road Jagatballavpur Munsirhat to Ichanagari at Jagatballavpur Block, Pacakage No-WB/09/17 Howrah under WBSRDA Howrah Division-I. |  |  | BILL/00975/2025-2026 |  | 06/11/2025 | 06/11/2025 | WBSRDA-I | 16.68 | 0 | 0 | 0
58 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "Godaripara - Dulepara L047" at Jagatballavpur Block, Pkg No WB/09/135, Howrah undert W.B.S.R.D.A. Howrah Division-I. |  |  | BILL/00088/2025-2026 |  | 28/04/2025 | 28/04/2025 | WBSRDA | 15.84 | 0 | 0 | 0
59 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Special repair work for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipeline for the PMGSY road "Ghoshpara to Khadarghat" at Jagatballavpur Block, Howrah under W.B.S.R.D.A. Howrah Division-I Package No. - WB/09/46. |  |  | BILL/00292/2025-2026 |  | 25/06/2025 | 25/06/2025 | WBSRDA-I | 26.01 | 0 | 0 | 0
60 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Special repair work (Bituminous Portion) for restoration of damaged pavement caused by laying of Public Health Engineering Directorate's pipe line for the PMGSY road "T05 Bramhapara - Aimachak and Naikul to Nabason Road L044" at Jagatballavpur Block, Pkg No WB/09/144, Howrah under W.B.S.R.D.A. Howrah Division-I. |  |  | BILL/00092/2025-2026 |  | 28/04/2025 | 28/04/2025 | WBSRDA | 14.89 | 0 | 0 | 0
61 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | The Augmentation Scheme Of Bargachia Pwss Under Howrah Division Application No- 100000128111 Reference ID- 860323061 SM Code- 14095 |  |  | BILL/03085/2024-2025 | 693 | 31/01/2025 | 31/01/2025 | WBSEDCL | 1.67 | 0 | 0 | 0
62 | HOWRAH |  | Electrical | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1008321283 Reference ID- 106898028 SM Code- 14095 |  |  | BILL/00959/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 25.1 | 0 | 0 | 0
63 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone III (TW-1 &TW-II), Zone-IVA (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000686/2022-2023 | 305/HD | 20/01/2023 | 25/07/2025 | B K ENTERPRISE | 69.42 | 50.09 | 72.16 | 100
64 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 13/04/2026 | HORIZEN | 10.11 | 4.33 | 42.82 | 56
65 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supplying fabrication of 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jack pushing method to Cross Water carrier Pipe (Between Node Point 134 to 153 of LDS drawing) between Patihal-Bargachia Station at KM HA-22/15-16 (35/15-16) (WL-58) and Pipe (Between Node Point 242 to 259 of LDS drawing) between Patihal-Bargachia Station at KM HA-22/23-24 (35/23-24) (WL-59) of Bargachia Zone-II Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. (SM/14095) | AE/SADAR | JE Sadar | ORD/000048/2025-2026 | 2339/HD | 14/05/2025 | 10/11/2025 | JOY GURU TRADING | 109.35 | 0 | 0 | 50
66 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Bargachia Zone-4A, Bargachia Zone-4B, Bargachia Zone-5 PWSS [SM/14059] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000990/2024-2025 | 218-A/HSSD | 24/02/2025 | 11/03/2025 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
67 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Bargachia Zone-9, Bargachia Zone-10 PWSS [SM/14059] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000991/2024-2025 | 221-A/HSSD | 25/02/2025 | 12/03/2025 | JHARNA ENTERPRISE | 0.57 | 0 | 0 | 100
68 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Bargachia Zone-1, Bargachia Zone-2, Bargachia Zone-3 PWSS [SM/14059] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000989/2024-2025 | 218/HSSD | 24/02/2025 | 11/03/2025 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
69 | HOWRAH |  | Howrah Division | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | SM/14095 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Jagatballavpur Block) | AE HQ | je_blk_ballyjag_how | ORD/000231/2025-2026 | 4129/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.78 | 0 | 0 | 100
Total | [13 empty] | 8063.11 | 3086.15 | 38.27