## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 22.21 | 0 | 0 | 0
2 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-VIII) Domjur (CT) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR | JE/RWS/Domjur | ORD/000232/2022-2023 | 85/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.88 | 0 | 0 | 100
3 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-VIII) Domjur (CT) water supply scheme, T.W. No.- III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000857/2023-2024 | 3429/ED | 11/08/2023 | 09/11/2023 | D. K. ELECTRIC | 10.74 | 0 | 0 | 100
4 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 99.73 | 0 | 0 | 0
5 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | new service connetion |  |  | BILL/02066/2023-2024 | 129 | 20/07/2023 | 20/07/2023 | WBSEDCL | 4.04 | 0 | 0 | 0
6 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-VIII) of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/BLK/DOM/HOW,je1_iu | ORD/000656/2022-2023 | 167/HD | 13/01/2023 | 27/02/2023 | AUXILIARY TUBEWELL DRILLERS | 38.56 | 0 | 0 | 40
7 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 4768/HD | 14/11/2024 | 14/11/2024 | Resource Division | 13.96 | 0 | 0 | 0
8 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Bill Document for payment of Wayleave facility charges for Application id: SER-KGP-2024-WL-37,Domjur-CT |  |  | BILL/00109/2024-2025 | BP-2024-25-48 | 07/05/2024 | 07/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.2 | 0 | 0 | 0
9 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Payment for Way Leave and Survey Charges Domjur Zone-VIII |  |  | BILL/01655/2023-2024 | BP-2023-24-734 | 27/03/2024 | 27/03/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0 | 0
10 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Bill Document for Payment of Wayleave facility charges for Application ID: SER-KGP-2024-WL-36,Domjur CT Bill Id-WL0051767 |  |  | BILL/00108/2024-2025 | BP-2024-25-49 | 07/05/2024 | 07/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.28 | 0 | 0 | 0
11 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Quotation money deposition for new service connection at Domjur(Zone-VIII) w/s scheme, Domjur(CT),Pwss, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008185198 Reference ID- 106810746 SM Code- 14155 |  |  | BILL/02126/2024-2025 | 570 | 13/11/2024 | 13/11/2024 | WBSEDCL | 9.33 | 0 | 0 | 0
12 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Payment for Way Leave and Survey Charges Domjur Zone-VIII |  |  | BILL/01657/2023-2024 | BP-2023-24-736 | 27/03/2024 | 27/03/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0 | 0
13 | HOWRAH | Domjur | Electrical | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-VIII) Domjur (CT) water supply scheme, T.W. No. I & II, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000253/2022-2023 | 920/ED | 22/02/2023 | 01/07/2025 | A.G. ENTERPRISE | 21.49 | 0 | 0 | 40
14 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Work Order for Construction of 600 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection For Domjur Zone-VIII, Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000034/2023-2024 | 1741/HD | 25/04/2023 | 11/07/2026 | M/S ASHIRBAD (INDIA) | 174.05 | 0 | 0 | 60
15 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Work Order for Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection) 2493 nos for Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte.(Part-II) For Node Section (135-136) to Node Section (800-801) | AE/SADAR | JE/BLK/DOM/HOW,je1_iu,je_blk_ballyjag_how | ORD/000093/2023-2024 | 1997/HD | 16/05/2023 | 05/05/2025 | ZAKIR HOSSIN MONDAL | 212.69 | 0 | 0 | 100
16 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Construction of 3 (Three) Nos.Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Domjur Zone-VIII, Construction of 2(Two) nos. Boundary Wall, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection) 2494 nos for Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. (Part-I) For Node Section (R-1- 1) to Node Section (565-566) | AE/SADAR | JE/BLK/DOM/HOW,je1_iu,je6/maad,je_blk_ballyjag_how | ORD/000188/2023-2024 | 3041/HD | 22/08/2023 | 16/11/2025 | TUSHAR KANTI GHOSH | 284.71 | 0 | 0 | 95
17 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 8.36 | 0 | 0 | 79
18 | HOWRAH | Domjur | Howrah Division | Ground water based water supply Scheme for Domjur (Zone-VIII) Domjur (CT) and its adjoining areas to Accommodate FHTC in Domjur Block, Diatrict-Howrah | SM/14155 | New | Supplying fabrication of 600 mm dia 10 mm thick MS casing pipe and Pushing of casing pipe by Hydraulic Jack pushing method to Cross Water carrier Pipe (Between Node Point 127 to 135 of LDS drawing) From Domjur station to Makardha station, KM/(TP/OHE) 11/03-11/04 (WL-37) of Domjur CT (Zone-8) Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. | AE/SADAR |  | ORD/000073/2025-2026 | 2756/HD | 12/06/2025 | 11/08/2025 | B. D. ENTERPRISE | 40.52 | 0 | 0 | 0
Total | [13 empty] | 954.92 | 0 | 0