## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 21.73 | 0 | 0 | 0
2 | HOWRAH | Domjur | Howrah Division | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 593/HD | 13/02/2023 | 13/02/2023 | Resource Division | 88.98 | 0 | 0 | 0
3 | HOWRAH | Domjur | Electrical | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | new service connection |  |  | BILL/02065/2023-2024 | 127 | 20/07/2023 | 20/07/2023 | WBSEDCL | 2.85 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | Quotation money deposition for new service connection at P.H No.-III of Bhandardah Pwss , Dist- howrah under ED PHED. App. No.-1007763810 SM/14197 |  |  | BILL/00468/2024-2025 | 120 | 17/05/2024 | 17/05/2024 | WBSEDCL | 6.68 | 0 | 0 | 0
5 | HOWRAH | Domjur | Howrah Division | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | Restoration Work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 0.00 Kmp to 1.90 Kmp (Due to Cutting for PHE water line) under Howrah Division in th e dist of Howrah during the year 2024-25. |  |  | BILL/00829/2024-2025 | BP-2024-25-496 | 27/11/2024 | 27/11/2024 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 9.52 | 0 | 0 | 0
6 | HOWRAH | Domjur | Howrah Division | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | Work Order for Laying distribution pipe line, Providing FHTC , Repairing of RCC Over Head Reservoir of capacity 350cum with allied work including supply of all labour & materials for Augmentation Of BHANDARDAH Water Supply Scheme at Domjur Block under Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000798/2022-2023 | 998/HD | 13/03/2023 | 27/12/2025 | P B ENTERPRISE | 754.4 | 487.37 | 64.6 | 80
7 | HOWRAH | Domjur | Howrah Division | Bhandardah PWSS with provision of FHTC connection | SM/14197 | New | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhandardaha PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000741/2022-2023 | 603/HD | 16/02/2023 | 02/04/2023 | M DHARA AND BROTHERS | 38.37 | 25.02 | 65.2 | 100
Total | [13 empty] | 922.52 | 512.39 | 55.54