## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Howrah Division | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 18.97 | 0 | 0 | 0
2 | HOWRAH | Panchla | Howrah Division | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Construction of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Foundation Design & All pipe Connection, 2(Two) Nos. Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Construction of Boundary Wall of 2nd Tube well site, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection-3079) for Jaynagar PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000214/2023-2024 | 3278/HD | 13/09/2023 | 13/08/2024 | REALIENCE CONSTRUCTION | 529.89 | 0 | 0 | 0
3 | HOWRAH | Panchla | Howrah Division | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Joynagar PWSS of Panchla Block under Howrah Division PHE Dte. | AE/SADAR |  | ORD/000978/2022-2023 | 1459/HD | 14/07/2022 | 13/08/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.11 | 99.37 | 100
4 | HOWRAH | Panchla | Howrah Division | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 54.61 | 0 | 0 | 0
5 | HOWRAH | Panchla | Electrical | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jaynagar water supply scheme, T.W. No. I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000027/2023-2024 | 1704/ED | 18/04/2023 | 17/07/2023 | DIPALI CONSTRUCTION | 22.8 | 15.41 | 67.61 | 30
6 | HOWRAH | Panchla | Howrah Division | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jaynagar PWSS(2 nos) & Banharishpur PWSS(2 nos) of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000800/2022-2023 | 1000/HD | 13/03/2023 | 14/11/2025 | PRANTIK DRILLING AGENCY | 68.83 | 0 | 0 | 25
7 | HOWRAH | Panchla | Howrah Division | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Sinking 1 no. 300 X 200 mm dia and 240 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 60 mtr. long PVC housing pipe & 200 mm dia. 150 mtr. long well pipe alongwith 3m blank pipe all complete including cost of materials under Jaynagar PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000071/2025-2026 | 2681/HD | 05/06/2025 | 31/01/2026 | AQUATECH ENGINEERS | 19.16 | 0 | 0 | 0
8 | HOWRAH | Panchla | Electrical | Jaynagar Piped Water Supply Scheme | SM/14865 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JAYNAGAR water supply scheme, TW No. III, Block: Panchla, District - Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003106/2024-2025 | 489/ED | 18/03/2025 | 16/06/2025 | DIPALI CONSTRUCTION | 11.3 | 0 | 0 | 0
Total | [13 empty] | 728.69 | 18.53 | 2.54