## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 10.53 | 0 | 0 | 0
2 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Sial Danga PWSS (Mouza-Sial Danga, Kumarpur, & Chak Patmura) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR |  | ORD/000075/2022-2023 | 1018/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 3.04 | 3.04 | 100 | 0
3 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Work Order for Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection, soil investigation & foundation design of Sealdanga PWSS at J.B.PUR Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000033/2023-2024 | 1736/HD | 25/04/2023 | 25/03/2024 | BISWAJIT BAG | 110.36 | 0 | 0 | 0
4 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Work Order for Laying Distribution Pipeline of Sealdanga PWSS at J.B.PUR Block of Howrah District under Howrah Division, P. H. E. Dte.(part-3) | AE/SADAR | JE Sadar | ORD/000014/2023-2024 | 1546/HD | 04/04/2023 | 02/08/2023 | BUILT INDIA | 93.16 | 32.91 | 35.32 | 35
5 | HOWRAH | Jagatballavpur | Electrical | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sealdanga water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000028/2023-2024 | 1705/ED | 18/04/2023 | 17/07/2023 | PADMA ENGINEERING CO. | 21.49 | 0 | 0 | 0
6 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 14.14 | 0 | 0 | 0
7 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Work Order for Laying Distribution Pipeline & Providing Functional Household Tap Connection((part-2), 550 nos of Sealdanga PWSS at J.B.PUR Blockof Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000013/2023-2024 | 1545/HD | 04/04/2023 | 19/03/2026 | M/S ASHIRBAD (INDIA) | 86.98 | 14.3 | 16.44 | 15
8 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Head Work Site& other tubewell site, Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) (550 Nos) For Sealdanga PWSS at J.B.PUR Blockof Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000135/2023-2024 | 2736/HD | 26/07/2023 | 28/12/2025 | SWASTIK ENTERPRISE | 123.64 | 0 | 0 | 20
9 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Construction of approach road and land Development at OHR site for Sealdanga PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000111/2025-2026 | 3131/HD | 14/07/2025 | 12/09/2025 | M/S SRIKANTA PATRA | 77.22 | 0 | 0 | 0
10 | HOWRAH | Jagatballavpur | Howrah Division | Sealdanga Piped Water Supply Scheme | SM/14866 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sealdanga PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000801/2022-2023 | 1001/H.D | 13/03/2023 | 01/05/2025 | R CONSTRUCTION | 25.64 | 0 | 0 | 100
Total | [13 empty] | 566.21 | 50.24 | 8.87