## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sonatala PWSS of Udaynarayanpur Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Amta II,JE/RWS/Udaynaryanpur,JE Sadar | ORD/000746/2022-2023 | 664/HD | 17/02/2023 | 19/03/2023 | LOKENATH ENTERPRISES | 26.22 | 22.69 | 86.53 | 100
2 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 7.84 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 14.77 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 3217/HD | 05/09/2023 | 05/09/2023 | Resource Division | 29.9 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Electrical | Sonatala Piped Water Supply Scheme | SM/14949 | New | QUOTATION OF NEW SERVICE CONNECTION FOR SONATALA W/S SCHEME, PH-II |  |  | BILL/02135/2023-2024 | 126 | 20/07/2023 | 20/07/2023 | WBSEDCL | 4.2 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Electrical | Sonatala Piped Water Supply Scheme | SM/14949 | New | QUOTATION OF NEW SERVICE CONNECTION FOR SONATALA W/S SCHEME, PH NO-I |  |  | BILL/02134/2023-2024 | 125 | 20/07/2023 | 20/07/2023 | WBSEDCL | 2.58 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Electrical | Sonatala Piped Water Supply Scheme | SM/14949 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sonatala water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000262/2022-2023 | 929/ED | 22/02/2023 | 23/05/2023 | TRIO CONCERN | 20.88 | 20.81 | 99.66 | 80
8 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 2.77 | 0 | 0 | 0
9 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site along with restoration work of damaged pipeline of SONATOLA Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS |  | ORD/000036/2025-2026 | 2276/HD | 07/05/2025 | 06/07/2025 | GUPTA ENTERPRISE | 63.76 | 0 | 0 | 0
10 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Rising Main & Inter Connection with both tube wells of SONATOLA Pipe Water Supply Scheme (SM/14949) at Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS |  | ORD/000038/2025-2026 | 2280/HD | 07/05/2025 | 21/06/2025 | GUPTA ENTERPRISE | 18.62 | 0 | 0 | 0
11 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Udaynarayanpur Block) (PART-B) | AE HQ |  | ORD/000226/2025-2026 | 4124/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
12 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Work Order for Construction of 500 Cum OHR including soil investigation, LDS with FHTC, Two Nos Pump House of SONATALA PWSS at Udaynarayanpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Amta II,JE/RWS/Udaynaryanpur | ORD/000024/2023-2024 | 1689/HD | 20/04/2023 | 16/10/2026 | GUPTA ENTERPRISE | 450.11 | 272.43 | 60.53 | 30
13 | HOWRAH | Udaynarayanpur | Howrah Division | Sonatala Piped Water Supply Scheme | SM/14949 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 13/04/2026 | HORIZEN | 13.59 | 1.04 | 7.65 | 70
Total | [13 empty] | 660.03 | 316.98 | 48.03