## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Joargarh water supply scheme, T.W. No. I, II & III, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000026/2023-2024 | 1703/ED | 18/04/2023 | 17/07/2023 | H.K.DAS & CO. | 32.55 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Preparation of DPR for Augmentation of Joargori PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000242/2022-2023 | 319/AE/USD | 16/08/2022 | 30/09/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.83 | 3.83 | 99.84 | 100
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 74.81 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 6.16 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Quotation money deposition for new service connection at Joargarh pwss ,T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007613302 Reference ID- 106525750 SM Code- 15186 |  |  | BILL/06654/2023-2024 | 23 | 05/04/2024 | 05/04/2024 | WBSEDCL | 5.13 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Quotation money deposition for new service connection at Joargarh pwss ,T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007614302 Reference ID- 106526159 SM Code- 15186 |  |  | BILL/06655/2023-2024 |  | 28/03/2024 | 28/03/2024 | WBSEDCL | 4.9 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | SM/15186 | Augmentation | Sinking of 05 (Five) nos Big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (UPVC & HDPE & DI) & Providing Functional Household Tap Connection (FHTC), Interconnection between tubewells and OHR and Construction of OHR of 700 cum and 400 cum capacity 20.0 m staging height along with pipe connection etc for SHERPUR PWSS in Amta-I Block and Augmentation of JOARGARH PWSS in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=8807] | AE/Ulu | JE-USD,JE/USD | ORD/000239/2023-2024 | 3488/HD | 29/09/2023 | 17/03/2026 | S.P. CONSTRUCTION | 1926.07 | 188.68 | 9.8 | 60
Total | [13 empty] | 2053.46 | 192.51 | 9.38