## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-II | Electrical | Matinala Piped Water Supply Scheme | SM/15285 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Matinala water supply scheme, T.W. No.- I & II, Block: Bagnan-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000261/2022-2023 | 928/ED | 22/02/2023 | 23/05/2023 | R.M.D TRADING. | 20.38 | 0 | 0 | 0
2 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Preparation of DPR for Augmentation of Matinala (Mellock Zone-I) PWSS, Bagnan-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/000225/2022-2023 | 317/AE/USD | 16/08/2022 | 30/09/2022 | MS SOBHA AND CO | 3.61 | 0 | 0 | 100
3 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 27.35 | 0 | 0 | 0
4 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 2979/HD | 17/08/2023 | 17/08/2023 | Resource Division | 26.58 | 0 | 0 | 0
5 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) at Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-A) | AE/Ulu | JE/USD | ORD/000882/2022-2023 | 1436/HD | 29/03/2023 | 27/07/2023 | BISWAJIT BAG | 163 | 0 | 0 | 100
6 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Sinking of 5 (Five) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Harop PWSS Zone -I (1 no) & Zone-II (2 nos) & Matinala PWSS (2 nos) of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE-USD,je/blk/bagn1,JE/USD | ORD/000249/2023-2024 | 3533/HD | 04/10/2023 | 03/12/2023 | AQUATECH ENGINEERS | 64.95 | 0 | 0 | 40
7 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Balance Laying of distribution pipeline Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Mellock) | AE/Ulu | JE/USD | ORD/000585/2023-2024 | 3104/AE/USD | 29/02/2024 | 14/04/2024 | BISWAJIT BAG | 13 | 0 | 0 | 100
8 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Balance Laying of distribution pipeline Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Matinala) | AE/Ulu | JE/USD | ORD/000687/2023-2024 | 3242/AE/USD | 12/03/2024 | 26/04/2024 | SUNIRMAN ENTERPRISE | 11.92 | 0 | 0 | 100
9 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Site preparation and partial land Development at HW site of Matinala PWSS of Bagnan-II Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu | JE/USD | ORD/000175/2024-2025 | 797/AE/USD | 09/09/2024 | 09/10/2024 | ADITYA HAZRA | 4.8 | 0 | 0 | 100
10 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Construction of switch room ( 3.60 m x 3.0 m) with water supply sanitary arrangement at 2nd tube well site of Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu | JE/USD | ORD/000185/2024-2025 | 769/AE/USD | 05/09/2024 | 20/10/2024 | D.C. CONSTRUCTION | 4.68 | 0 | 0 | 100
11 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 10.29 | 0 | 0 | 0
12 | HOWRAH | Bagnan-II | Electrical | Matinala Piped Water Supply Scheme | SM/15285 | New | Quotation for new service connection for Matinala Water Supply Scheme, PH NO- II, in the district Howrah under Electrical Division, PHE Dte. ( SM/15285), Reference Id- 106538620 , Application no- 1007634961 |  |  | BILL/00087/2024-2025 | 40 | 09/04/2024 | 09/04/2024 | WBSEDCL | 4.07 | 0 | 0 | 0
13 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-II & Uluberia-II Block) | AE HQ |  | ORD/000222/2025-2026 | 4120/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
14 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ | je_blk_ballyjag_how | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 01/11/2025 | TECH VISION | 21.25 | 0 | 0 | 0
15 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-C) | AE/Ulu | JE/USD | ORD/000763/2022-2023 | 705/HD | 22/02/2023 | 12/02/2025 | SUNIRMAN ENTERPRISE | 66.28 | 0 | 0 | 90
16 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-D) | AE/Ulu | JE/USD | ORD/000764/2022-2023 | 706/HD | 22/02/2023 | 13/04/2025 | USHA CONCERN | 73.23 | 0 | 0 | 100
17 | HOWRAH | Bagnan-II | Howrah Division | Matinala Piped Water Supply Scheme | SM/15285 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube well & Construction of 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation for MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-B) | AE/Ulu | JE/USD | ORD/000840/2022-2023 | 1141/HD | 21/03/2023 | 10/03/2025 | ADITYA HAZRA | 218.71 | 0 | 0 | 100
Total | [13 empty] | 738.88 | 0 | 0