## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-I | Electrical | Mollar Chak Piped Water Supplu scheme | SM/15288 | New | Quotation for new service connection of Mollarchak Mini water supply scheme, Amta- I , Howrah |  |  | BILL/06038/2023-2024 | 735 | 07/02/2024 | 07/02/2024 | WBSEDCL | 0.09 | 0 | 0 | 0
2 | HOWRAH | Amta-I | Howrah Division | Mollar Chak Piped Water Supplu scheme | SM/15288 | New | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | AE/Ulu | JE/USD | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 23/01/2026 | MONDAL PRECISION PVT. LTD. | 330.32 | 21.47 | 6.5 | 80
Total | [13 empty] | 330.41 | 21.47 | 6.5