## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Howrah Division | Sankhali Piped Water Supply Scheme | SM/15289 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shankhali PWSS of Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000799/2022-2023 | 999/HD | 13/03/2023 | 27/04/2023 | SPG ENTERPRISES | 25.7 | 23.41 | 91.09 | 100
2 | HOWRAH | Panchla | Howrah Division | Sankhali Piped Water Supply Scheme | SM/15289 | New | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Shankhali PWSS of Panchla Block under Howrah Division PHE Dte. | AE/SADAR |  | ORD/000977/2022-2023 | 1456/HD | 13/07/2022 | 12/08/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.63 | 2.59 | 98.24 | 100
3 | HOWRAH | Panchla | Howrah Division | Sankhali Piped Water Supply Scheme | SM/15289 | New | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 4.34 | 0 | 0 | 0
4 | HOWRAH | Panchla | Electrical | Sankhali Piped Water Supply Scheme | SM/15289 | New | NEW SERVICE CONNECTION AT SANKHALI PWSS P.H No.-II |  |  | BILL/02908/2023-2024 | 207 | 24/08/2023 | 24/08/2023 | WBSEDCL | 3.51 | 0 | 0 | 0
5 | HOWRAH | Panchla | Electrical | Sankhali Piped Water Supply Scheme | SM/15289 | New | NEW SERVICE CONNECTION AT SANKHALI PWSS P.H No.-I |  |  | BILL/02907/2023-2024 | 205 | 24/08/2023 | 24/08/2023 | WBSEDCL | 3.2 | 0 | 0 | 0
6 | HOWRAH | Panchla | Electrical | Sankhali Piped Water Supply Scheme | SM/15289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sankhali water supply scheme, T.W. No.- I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000260/2022-2023 | 927/ED | 22/02/2023 | 08/04/2023 | SRI KRISHNA NIRMAN | 20.35 | 19.65 | 96.56 | 90
7 | HOWRAH | Panchla | Howrah Division | Sankhali Piped Water Supply Scheme | SM/15289 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 6.52 | 0 | 0 | 0
8 | HOWRAH | Panchla | Howrah Division | Sankhali Piped Water Supply Scheme | SM/15289 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 12.48 | 0 | 0 | 62
9 | HOWRAH | Panchla | Howrah Division | Sankhali Piped Water Supply Scheme | SM/15289 | New | Work Order for Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m),Construction of Boundary Wall at Head work Site, Others site Boundary Wall, Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/2/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Estimate of Providing FHTC (Functional Household Tap Connection) For Sankhali PWSS at Panchla Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000015/2023-2024 | 1595/HD | 12/04/2023 | 22/09/2025 | REALIENCE CONSTRUCTION | 236.2 | 127.02 | 53.78 | 20
Total | [13 empty] | 314.93 | 172.66 | 54.83